## Slide 1: Task 9.2 Business Pilots
EOSC hub kick-off, 9.01, Amsterdam
Marcin Płóciennik, PSNC

## Slide 2: Agenda
  Overview of 9.2
  Overview of 9.2.1
  Business Pilots
  Overview of 9.2.2
  Deliverables/Milestones
  First year work plan (PM1-PM12)
  KPI and Metrics
  Links

## Slide 3: Overview of 9.2
Composed of two subtasks:
  Initial Business Pilots
  Open Lab
Objectives:
  Coordinating pilots
  Ensuring access to services and tech support
  Assessing and validating results
  Identifying additional experiments
Partners:
  Lead Partner: PSNC(13+11.5PM); Participants: EGI.eu(12PM), CINECA(12PM), Ecohydros(14 PM), Moxoff(20PM), Yottacle(15.5PM), Action Modulers(14PM), Koma Nord(12.5PM), IDEGO(13.5PM), Hidronav(15.6PM), CSIC(2PM), SUITE5(9.2PM), AIDIMME(17PM), UCL(7PM)

## Slide 4: Overview of 9.2.1
Background:
  The initial demonstrators of the DIH
  Pilots with different domains and have different technical requirements
  introducing added value services and clear exploitation and long-term business plans
Objectives:
  Coordinating 6 initially selected pilots
  Ensuring access to services and tech support: Providing first level support and monitoring progress
  Defining IPR
  Assessing and validating results
Partners:
  Lead Partner: PSNC; Participants: EGI.eu, CINECA, Ecohydros, Moxoff, Yottacle, Action Modulers, Koma Nord, IDEGO, Hidronav, CSIC, SUITE5, AIDIMME, UCL

## Slide 5: EOSC-hub Joint DIH (WP9): Initial Business Pilots
1.) CyberHAB (SME: Ecohydros)
Environment: Early warning and integral management of Harmful Algae Blooms exploiting Data Cloud Services (DCS) and key processes required (data processing, modelling, image integration).
2.) Moxoff (3SME:Moxoff, Yottacle. Action Modulers + CINECA)
Sport and biomedicine: Develop mobile-friendly cloud platform for data-driven video analysis processing
3.) Bot Mitigation Engine (2SME:Koma Nord, IDEGO + PSNC)
Security: Prevent on-line services from botnets attacks like: Web Scraping, Online Fraud, Digital Ad Fraud, Web Application, Security, Spam.
4.) Suite5Pilot (2 SMEs + CINECA)
Furniture: Enterprise Analytics Platform-as-a-Service
5.) ACTION Seaport (SME: Action Modulers)
Seaports: Improve safety, environmental and operational ports through a mobile-friendly platform
6.) DS-DRACO (SME: Hidronav + CESGA)
Space Weather: Data Services to develop an appropriate cloud super computational pilot framework for the future commercialization of the DRACO data.

## Slide 6: Initial pilots expected results and exploitation

## Slide 7: Overview of 9.2.2 Open Lab
Background:
  This activity focuses on developing new success stories and experiments for the DIH through different channels (like the pilots or data challenges) through open innovation during the second half of the project.
Objectives:
  Identifying new possible use cases, experiments & collaboration opportunities and work with consortium experts to provide technical support them
  Disseminating initial experiments via use cases and success stories to attract new customers and foster onboarding (with WP3) and inputs to WP2 (strategy and exploitation)
  Facilitating access to the required services
Partners:
  Lead: CINECA, Participants: PSNC, EGI.eu

## Slide 8: EOSC-hub Joint DIH (WP9): Objectives
  Deliverable D9.1, Month3
    Title: Initial Business Pilots Overview & Work Plans
    Lead partner: PSNC
  Deliverable D9.3, Month21
    Title: Business Pilots Results
    Lead partner: PSNC
  Milestones M9.1, Month24
    Title : Business Pilot Success Stories
    Lead partner: PSNC
  Involved partners: PSNC, EGI.eu, CINECA, Ecohydros, Moxoff, Yottacle, Action Modulers, Koma Nord, IDEGO, Hidronav, CSIC, SUITE5, AIDIMME, UCL

## Slide 9: 9.2: First Year Work Plan
  First year work plan (PM1-PM12)
    Month1: Work organization (list including all the BP, cyclic telcos) and procedures (dealing with the pilots requests)
    Month1- Month3: Deliverable D9.1
      Title: Initial Business Pilots Overview & Work Plans
    Month2- Month3: Identify technical requirements from the pilots
    Month 4 – make sure that the internal architectures are established including all the necessary EOSC-hub services?
    Month 6, Month 9 – progress check
    Month 12: results ready for early adopters
  PM 12-21
    finalize the pilots
    Deliverable D9.3
    9.2.2: developing new success stories and experiments

## Slide 10: D9.1
Deliverable D9.1, Month3
  Title: Initial Business Pilots Overview & Work Plans
  “This report provides an introduction to the management of the business pilots and details the individual activity plans of each comprising objectives, timelines and expected results. Communication of initial activities will be limited to the Joint DIH public webspaces. Upon conclusion of each pilot, a polished use case will be published for external consumption.”
  Initial TOC to be proposed next week
  Questionnaire for the Pilots to define necessary details beginning of the February

## Slide 11: 9.2: KPI and Metrics
KPIs defined during proposal writing:
  KPI04: # published business pilot success stories
Related KPIs:
  Dissemination:
    Participate in industry-related > E.g. GreenPort Conference & Business2Sea (ACTIONport) or events International Water Association (Ecohydros) or Big Data from Space Conference (Hidronav)
    Promote the outputs of the > 1 flyer showcasing each business pilot business pilots > 1 business use case publication
    Write use cases to illustrate > 1 use case per business pilot, focused on usage added value of business pilots

## Slide 12: 9.2: KPI and Metrics (part of the table)
WPw | Success criteria | Indicator | Baseline | Target | 
Work package number | What is your strategic objective with regards to the exploitation of the result? (e.g. increase the user base, achieve sustainable funding) | Could you please give us an indicator to measure how you are succeeding in exploiting the result? | What is the value of the measure at the at the beginning of the project? | What is the ideal value you want to reach by the end of the project? | What is the stretch value you want to reach by the end of the project?
WP9 | Acceptance by relevant institutions | Subscription of relevant institutions | 0 | 5 | 3
WP9 (Moxoff/Yottacle) | Automatic video processing | Hours for the processing of one training session (100 videos) (end of pilot: Dec 2018) | 10 | 0.5 | 2
WP9 (Moxoff/Yottacle) | Increase the user base in the sport field | Number of users of the SaaS (end of pilot: Dec 2018) | 2 | 50 | 35
WP9 (Moxoff/Yottacle) | Extend the user base to other industrial sectors | Number of new industrial sector (end of pilot: Dec 2018) | 0 | 1 | 1
WP9 (AM) | Increase Performance & accuracy in hydrodynamics: distribution of 3D high resolution forecasting system for hydrodynamic conditions running in a fast way | Time needed (h) for a 3-day forecast run in a single Port, with a 75 m spatial resolution | 12 | 2 | 4
WP9 (AM) | Increase Performance & accuracy in meteorology: distribution of 3D high resolution forecasting system for meteorological conditions running in a fast way | Time needed (h) for a 5-day forecast run in an area covering a single Port, with a 1 km spatial resolution | 12 | 2 | 4

## Slide 13: 9.2: Links
Links
  Network of contacts for potential collaboration
    Needed to be identified for the 9.2.2, but in advance
  From 9.2 task to other project WPs
    9.2.1 will need to collaborate with WP4, WP5, WP6 services to support the use cases (detailed matrix needed to be done)
    9.2.2 will disseminate initial experiments via use cases and success stories to attract new customers and foster onboarding (with WP3) and inputs to WP2 (strategy and exploitation)

## Slide 14: Open Points
Durations: The pilots according to open call organize – 18 months, deliverable regarding the final results – month 21, first deliverable – month 3, KPI asks about end of the project, what should be involvement period of the pilot partners? Most of the information -> month 18, ask to leave some resources afterwards
Technical trainings for the business pilots? How to pass knowledge?  1-1 meetings
If not yet there, from the project we will need procedures, template and tools …. (and we need temporary solutions)
Procedures for handling pilots requests-> via 9.2

## Slide 15
Thanks! Questions?