## Slide 1: WP3 Innovation Management, Communication and Stakeholder Engagement
Sara Garavelli, Trust-IT Services
s.garavelli@trust-itservices.com
Amsterdam, 9 January 2018

## Slide 2: Partners introduction - roundatable
All partners - What you bring specifically to the table & your role within the WP3

## Slide 3: Outline
Adoption of the WP3 meeting agenda
Expected Outputs of the meeting
WP3 Objectives
WP3 structure & partners’ roles
WP3 partners’ effort
Deliverables & Milestones
WP3 meetings, procedures & tools
Risks & Mitigation Plan
WP3 quality metrics

## Slide 4: WP3 Meeting - Agenda
15:30 – 15:45 WP3 coordination: Welcome & Overview, S. Garavelli
15:45 – 16:00 Task 3.1 Innovation Management S.Andreozzi
16:00 – 16:30 Task 3.2 Engagement F. Aguilar
16:30 – 17:00 Coffee break
17:00 – 17:30 Task 3.3 Communications S. Coelho
17:30 – 17:45 Task 3.4 Events S. Garavelli
17:45 – 18:15 Task 3.5 Branding C. Piagentini
18:15 – 18:30 AOB

## Slide 5: Expected Outputs of the meeting
WP Work Plan. Detailed 12 month work plan specifying distribution of activities by task. https://docs.google.com/spreadsheets/d/1COZzwEArRexybn1zXx9D14vXNKWqAlH7mnWEWMuIZ0M
Preliminary definition of lead authors for each deliverable https://confluence.egi.eu/display/EOSC/Deliverables
Preliminary definition of milestone owners in PY1 https://confluence.egi.eu/display/EOSC/Milestones
Define WP regular meetings https://indico.egi.eu/indico/category/211/
Define preliminary quality metrics https://docs.google.com/spreadsheets/d/1e7mpWgoP45wLNz_OTZn31cekUckYAKxVSqhaexZChFU/edit#gid=0
Define team membership https://confluence.egi.eu/display/EOSC/AMB
Identify the Key Exploitation Results (KERs) https://confluence.egi.eu/display/EOSC/T5.1+Identification%2C+Authentication%2C+Authorisation+and+Attribute+Management
EOSC-hub/OpenAIRE Advance collaboration - Assessment and impact on the WP work plan

## Slide 6: WP3 Objectives
  Develop & implement a stakeholder-oriented dissemination & engagement strategy
  Develop & implement the project's communications plan to support dissemination & engagement
  Ensure that project results are captured, disseminated and exploited
  Organise and roll-out a series of EOSC-hub events for all key stakeholders
Make sure that a joint communication plan is created and executed with OpenAIRE-Advance

## Slide 7: EOSC-hub / OpenAIRE-Advance
Complementary grants in EINFRA-12
  Mandated by the work programme to deliver joint activities
    Strategy, Governance, Communications/Outreach/Training/Support, Service Integration
Initial preliminary joint activity plan
  https://indico.egi.eu/indico/event/3511/overview
Actions
  Jan (WP2/5/6/7/8/10): Prioritization of technical integration activities according to impact, demand (define use cases) and available effort in each task
  Feb: update of joint activity plan
  March: finalization of joint activity plan
Source: Tiziana Ferrari, EGI
Joint communication plan T3.3
Branding T3.5
Web-platform T3.5

## Slide 8: WP3 structure & Partners’ roles
WP3 Innovation Management, Communication and Stakeholder Engagement |  | Resources
T3.1: Innovation Management: Dissemination, IPR and Exploitation | Lead Partner: EGI.eu | Task Leader: sergio.andreozzi@egi.eu Task contributors: roberta.piscitelli@egi.eu
T3.2: Stakeholder Engagement Programme: EOSC-hub Community | Lead Partner: CSIC Participants: CINECA, EGI.eu | Task Leader: isabel.campos@csic.es /aguilarf@ifca.unican.es? Task contributors: d.testi@cineca.it, Gergely.Sipos@EGI.eu
T3.3: Communications | Lead Partner: EGI.eu Participants: CINECA, CSIC, TRUST-IT | Task Leader: sara.coelho@egi.eu Task Contributors: iulia.popescu@egi.eu, s.garavelli@trust-itservices.com, c.piagentini@trust-itservices.com, d.testi@cineca.it, isabel.campos@csic.es
T3.4 EOSC-hub Events | Lead Partner: TRUST-IT Participants: EGI.eu | Task Leader: s.garavelli@trust-itservices.com Task Contributors: c.piagentini@trust-itservices.com, r.carrillo@trust-itservices.com, sara.coelho@egi.eu, iulia.popescu@egi.eu
T3.5 Branding & web-based support tools | Lead Partner: TRUST-IT | Task Leader: c.piagentini@trust-itservices.com Task Contributors: s.garavelli@trust-itservices.com, r.carrillo@trust-itservices.com, l.difiore@trust-itservices.com

## Slide 9: Partners’ efforts
Partner | T3.1 | T3.2 | T3.3 | T3.4 | T3.5 | Total Effort
CINECA | 0 | 12 | 3 | 0 | 0 | 15
CSIC | 0 | 15 | 3 | 0 | 0 | 18
EGI Foundation | 18 | 6 | 30 | 3 | 0 | 57
TRUST-IT Services | 0 | 0 | 24 | 12 | 12 | 36
Total | 18 | 33 | 60 | 15 | 12 | 138
4 partners
138 PMs

## Slide 10: WP3 Deliverables
Deliverable Title | Lead Beneficiary | Author | Reviewer | Type | Dissemination Level | Due Date
D3.1 EOSC-Hub Communication & Stakeholder Engagement Plan | CSIC | I.Campos | ??? | Report | Confidential | 4
D3.2 Innovation management plan | EGI Foundation | R. Piscitelli | ??? | Report | Public | 8
D3.3 Interim report on dissemination and exploitation of project results | EGI Foundation | R. Piscitelli | ??? | Report | Public | 18
D3.4 Final report on dissemination and exploitation of project results | EGI Foundation | R. Piscitelli | ??? | Report | Public | 36
D3.5 Communication & Stakeholder Engagement: Final Report | CSIC | I.Campos | ??? | Report | Public | 36
5 deliverables (2 in the first 12 months)

## Slide 11: WP3 Milestones
Milestone Title | Lead Beneficiary | Owner | Means of verification | Due Date
M3.1 EOSC-hub logo, templates and project brand | Trust-IT | C.Piagentini | EOSC-hub graphic design | 1
M3.2 EOSC-Hub Web Platform launch | Trust-IT | C.Piagentini | Package available | 3
M3.3 Workshop on innovation management | EGI Foundation | R.Piscitelli | Workshop held | 6
M3.4 Initial Evaluation of EOSC-hub Community | CSIC | I.Campos | Report available | 6
M3.5 Organisation of first EOSC-hub flagship event | Trust-IT | S. Garavelli | Event held | 12
M3.6 Intermediate evaluation of EOSC-hub Community | CSIC | I.Campos | Report available | 12
M3.7 Innovation Management Webinar | EGI Foundation | R.Piscitelli | Webinar held | 16
M3.8 Final Evaluation of EOSC-hub Community and perspective | CSIC | I.Campos | Report available | 24
M3.9 Organisation of Second EOSC-hub flagship event | Trust-IT | S. Garavelli | Report available | 28
M3.10 Innovation Management Webinar | EGI Foundation | R. Piscitelli | Webinar held | 30

## Slide 12
Meetings:
  Monthly calls (1 hour) with the WP3 task leaders (or a deputy) one week before the AMB meeting
    Scope: discuss major achievements, activities planned for the upcoming month and potential issues/plan deviations, check the activity report
    Where: Gotomeeting (Trust-IT responsible for circulating agenda and minutes)
  Team B calls for the OpenAIRE collaboration
  Innovation Management? Stakeholder Engagement?
Procedures & Tools:
  WP3 Mailing list for all the WP communications (Do we need mailing lists for any tasks?)
  Other mailing list: events@ ; communications@ ; info@
  Confluence to monthly report activities performed in the tasks – before the AMB call https://confluence.egi.eu/display/EOSC/2018-01-05+Activity+report+example
  Comm & Diss matrix https://confluence.egi.eu/display/EOSC/Dissemination+Activities
WP3 meetings, procedures & tools

## Slide 13
Agreement with OpenAIRE-Advance on joint branding and web-platform
Budget for events
Reluctance of contributing to IM in terms of exploitation and concrete plans
Risks and mitigation plans

## Slide 14: WP Quality metrics
Owner | Task | Description | Baseline | Summed/averaged | Measurement | How data is gathered / Data source | Target PY1 | Target PY2 | Target PY3 | Unit | Polarity | Comment
example: Malgorzata Krakowian | 1.3 | Number of delay days of Deliverables' submission | 0 | Averaged | As value for the whole reporting period | manual counting from https://confluence.egi.eu/display/EOSC/Deliverables | 0 | 0 | 0 | # | Down |