## Slide 1: T3.4 EOSC-hub Events
Sara Garavelli, Trust-IT Services
s.garavelli@trust-itservices.com
Amsterdam, 9 January 2018

## Slide 2: Outline
Objectives
Partners’ roles & effort
Task results & key exploitable results
Activity Plan M1-M12
Deliverables & Milestones
KPIs & Metrics
Risks & Mitigation Plan

## Slide 3: Objectives
  Organisation of 2 flagship EOSC-hub events (M12, M28) for all stakeholders to interact and exchange information and updates.
  Support for other WPs and tasks to organise and manage training, workshops, meetings, etc. to engage with external stakeholders.
  Coordinate participation to 70+ 3rd party events for all stakeholder target audiences.

## Slide 4
Partner | Role | Efforts
TRUST-IT | Lead Partner | 12 PMs
EGI | Participant | 3 PMs
Partners’ roles & effort
  The Team:
  Sara Garavelli, Trust-IT Services (Task Leader)
  Caterina Piagentini, Rob Carrillo, Trust-IT Services
  Sara Coelho, Iulia Popescu, EGI

## Slide 5: Task results & activity plan
3 public events:
  EOSC-Hub Launch Event (European Commission), 21 February 2018, Brussels (TBC)
  e-infrastructure public day co-located with the upcoming ”all-hands” meeting, 16-17 April , (Malaga) TBC
  EOSC-Hub flagship event – DI4R2018, early October 2018, Austria (TBC)
Support the organisation of the internal meetings
  EOSC-hub “All-hands” meeting, 17-20 April 2018, (Malaga)
Coordination of participation to c.a. 25 third-party events https://docs.google.com/spreadsheets/d/12TvO1cFxx82LamgzC4odlVUR6wRfuvqdQIwQ0a3Pq_c/edit#gid=1204053110

## Slide 6: e-infrastructure public day & “all hands” meeting, 16-20 April 2018
Dates & location identification by end of January 2017. The selection depends on the budget. Budget available 17K€ (WP1 budget to be confirmed)
Proposed Agenda:
  Day 1: public event where EUDAT, EGI, Indigo can showcase their services & results.
  Day 2-3-4: EOSC-hub internal meeting
Open points:
  No budget has been allocated for the public day. This day has to be sponsored by the participating initiatives and/or via registration fees
  No budget has been allocated for the “all hands” meeting. This meeting will be covered if possible totally with the 17K€ made available by WP1
TRUST-IT
TRUST-IT/EGI

## Slide 7: DI4R2018
  Call with GEANT, PRACE & RDA already scheduled on 31st January 2018 to agree on the participation to event and to identify potential dates/venues
  February 2018
    Programme Committee set up
    Announcement
    Registration opening (with website revamp & technical improvement)
  Early October 2018 - event takes place (M3.5 Organisation of first EOSC-hub flagship event)
TRUST-IT/EGI

## Slide 8: Deliverables & Milestones (M1-12)
 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
M3.5 Organisation of first EOSC-hub flagship event |  |  |  |  |  |  |  |  |  |  |  | X

## Slide 9: KPIs & Metrics
  # participants to the events
  # new potential users/community engaged

## Slide 10: Risks
20K x year
  DI4R
  1 All hands meeting
  Public einfra day
Budget Owner | Description | Budget
TRUST-IT | 2 EOSC-HUB Flagship Events | 60,000
TRUST-IT | Audio Visual Support (at 2 flagship events) | 4,000
TRUST-IT | EOSC-Hub @ Third Party Events (over 70) | 45,000
EGI | EOSC-Hub Communication Material | 57,500
No budget allocated for internal meetings
Budget allocated only for 2 flagship events
Mitigation plan:
  Registration fee
  Sponsors
  Budget coming from A/V support, 3rd party events, Comm. Material

## Slide 11: Events budget for 2018 - simulation
Events | Event Cost (€) | Budget Source | Total Budget available (€) | Budget Owner
Public launch | 0 | Venue offered by the EC |  | 
Public einfra day | c.a. 20K | Sponsored by participating initiatives EOSC-Hub Communication Material | 5K€ each (15K€) | Participating initiatives
All Hands meeting | OPTION A (hosted for free by a partner) 20K | WP1 2 EOSC-HUB Flagship Events | 17,000 5,000 | EGI TRUST-IT
All Hands meeting | OPTION B (venue to be rented) c.a. 50K | WP1 2 EOSC-HUB Flagship Events Registration fee? | 17,000 5,000 150€ x person (considering 200 ppl) | 
Innov management workshop | 4K | Innovation Management Workshop | 4,000 | EGI
DI4R2018 | 20K€ (EOSC-hub contribution) | 2 EOSC-HUB Flagship Events EOSC-Hub Communication Material | 15,000 5,000 | TRUST-IT EGI