## Slide 1: T11.4 Training about common and federated services
Leader: EGI.eu
Participants: CNRS, CYFRONET, GRNET, IASA, IISAS, INFN, SURFsara, CCFE
Duration: PM1-PM36
Dr Yin Chen, yin.chen@egi.eu, EGI Foundation
EOSC-Hub Kick-off, 9-11 Jan 2018, Amsterdam

## Slide 2: About the Task (DoW)
Objectives: Define and deliver training contents about common federated services for supporting scientific activities of TS, CCs and research communities
Descriptions:
  Develop and deliver training content about the common/federation services
  Relevant to TS and CCs, and external research communities
  Provide training about all services in Table 2
Milestones: Training Programme of 1/2 project year; M3/12; Training Programme online
Deliverables: Contributed D11.1, D11.3, D11.4, D11.5

## Slide 3: Issues To Be Clarified
ITBC#1: Contacts and PMs of each party in T11.4? Are they already the contact points of development WPs?
ITBC#2: How to collaborate with the following activities in T11.1
  T11.1: Maintain a catalogue of training events, training materials …
  T11.1: Provide a system for deployment and configuration of training env
  T11.1: Provide surveys and feedback forms
  T11.1: (9K for training events)
ITBC#3: Deliverables: which tasks? Which format?
  D11.1: Training materials about common services and thematic Services; Oth; M12: first year training plan -> T11.1, T11.4, T11.5
  D11.2: Training materials about competence center services; R; M24 -> T11.5
  D11.3: Updated Training materials about common service, thematic and competence services; Oth; M34; EGI.eu -> T11.1, T11.4, T11.5
  D11.4: Second Report on training activities, infrastructure and materials; R; M24 -> T11.1, T11.4, T11.5
  D11.5: Updated training materials about common, thematic and competence services; Oth; M34 -> T11.1, T11.4, T11.5
ITBC#4: Milestones in what formats?

## Slide 4: Table 2: EOSC-Hub service catalogue
Common
EGI HTC
EGI Cloud Compute
EGI Cloud container
DIRAC4EGI
EGI Online storage
EGI DataHub
B2HANDLE
B2FIND
B3DROP
B2SAFE
B2STAGE
B2SHARE
B2NOTE
Federation Services (13)
Accounting
ARGO
CheckIn
GGUS
GOCDB
Marketplace
Ops Portal
RC Auth
SPMT
DPMT
B2ACCESS
TTS
SVMON
Collaborative services (2)
AppDB
Repositories
Thematic Services (9)
ECAS
DARIAH SG
OPENCoastS
GEOSS
EO Pillar
WeNMR
DODAS
LifeWatch
CMI
Services (25)
ETDR
Sensitive Data Service
Advanced IaaS
TOSCA for Heat
OPIE
Synergy
BDII
IM
PaaS Orchestrator
CVMFS
IAM
WaTTS

## Slide 5: 1st Year Trainings
Objectives: Help TS, CC to choose right services to work with
Main Targeting Audience: TS and CCs but not exclusive
Time lines:
  Plan: work with T11.1, schedule of 1st year trainings by M3
  First set of training contents about common services: by M12
  Priority training delivery: by M6
  Other training delivery: by M12
Levels: Introduction and advanced
Training Scope:
  Common Services (25)
  Collaborative Services (2)
  Federated Services (12)
Formats:
  Contents (Slides/Guidance/User manuals/Recordings/VMs/Containers): each service should have, need to discuss with T11.1 which platform to use
  Webinars: popular requested by TS/CC (by survey)
  F2F trainings:
    Advanced level including hand-on sessions
    Popular requested by TS/CC
    Co-organise with EOSC-Hub conferences: Apr, Nov??

## Slide 6: 2nd Year Trainings
Objectives:
  Updates TS, CCs members with new developments
  Promote EOSC-Hub services for TS, CC communities and outsiders
Main Targeting Audience: TS, CCs, and their research communities
Time lines:
  Plan: work with T11.1, schedule of 2nd year trainings by M12
  Update of training contents: by M24
  Training delivery: by M24
Levels:
  Advanced (for TS, CCs members)
  Introduction (for others)
Formats:
  Webinars: popular requested by TS/CC (by survey)
  F2F trainings:
    Advanced level including hand-on sessions
    Popular requested by TS/CCs
    Co-organise with EOSC-Hub conferences,
    Work with T11.5, identify suitable TS, CCs community conferences and training events
  Contents (Slides/Guidance/User manuals/Recordings/VMs/Containers): updates

## Slide 7: 3rd Year Trainings
Objectives:
  Complete and maintain quality training materials for EOSC-Hub final services
  Promote EOSC-Hub services to TS, CCs and external research communities
  (Sustainability)
Main Targeting Audience: all
Time lines:
  Update of training contents: by M36
  Training delivery: by M36
Levels: all
Formats:
  Contents (Slides/Guidance/User manuals/Recordings/VMs/Containers): updated and strategies for sustainability, e.g. e-learning platform, on-line courses etc.
  Webinars and F2F trainings: also including external conferences

## Slide 8
https://docs.google.com/spreadsheets/d/1vHu0T-o-sd72cVkPGOxUI0UFA2p96FtEJenqd5ZkXAU/edit?usp=sharing

## Slide 9: Creation of Training Contents
Provided by service owners
T11.4 to provide templates and guidance:
  Slides: ppt template
  Recordings: guidance for video
  Guidance/user manual: templates for wiki
  VMs/Containers: guidance
T11.4 to monitor the progress
  Plan, responsible staff, timely completion
  Quality

## Slide 10: Organisation of training events
Training plan
  Plan description
  Plan preparation check list
Training delivery
  Event advertising and communication
  Training event organization
  Training and feedback collection
Training evaluation
  Knowledge learning: e.g., exam/quiz results
  User Feedback: feedback analysis
  Impacts, e.g., service adoption, promote training to communities etc.
Training Record Template (use tool such as Confluence)

## Slide 11: Training Plan and Preparation
Training planning: Completion and Submission PLAN part, no later than 1 month prior to events
Training Preparation: check-list and links
  Materials (VMs/containers/slides/guides): completed and reviewed
  Advertising message: completed and reviewed
  Event webpage: created and online
  Event is promoted via right communication channels:
  Event facilities: arranged
  Registration and logistic information: provided
  Request for trainees: provided
  Involved people: confirmed
  (Budget): approved

## Slide 12: Training Delivery
Pre-training activities
  Check with event facilities
Training activities
Post training activities:
  Upload materials to the event webpage
  Collect feedback forms
  Clean up e-Infra env after planned time
  Complete training record (template check list and links)

## Slide 13: Training Evaluation
Recommend to create quiz or exam for each course
Analyse training feedback
Tracking of training impacts, e.g., adoption, coming back trainees, bring new trainees etc.

## Slide 14: Tools and Templates
Catalogue of training events, materials (discuss with T11.1)
  Internal use
  Public use, e.g., towards a sustainable e-learning platform
Training material template
  For wiki
  For slides
  For user manual/guidance
  For video
Training record template (plan, preparation, delivery, evaluation)
Training feedback form (discuss with T11.1)
Training event page
Training advertising channels (WP7, 8, 9, communication team)
Users database and training mailing list
Trainers database

## Slide 15
Questions and Comments?

## Slide 16: T11.5 Domain-specific training to data providers and data scientists
Leader: EGI.eu
Participants: ASTRON, CESNET, CIRMMP, CCMC, CNR, CNRS, CSC, DKRZ, EISCAT, EMBL-EBI, GFZ, GWDG, IFREMER, INFN, LNEC, MEEO, MTA-SZTAKI, MU, SNIC, Sinergise, SURFsara, Terradue, USE, ASGC
Duration: PM1-PM36
Dr Yin Chen, yin.chen@egi.eu, EGI Foundation
EOSC-Hub Kick-off, 9-11 Jan 2018, Amsterdam

## Slide 17: About the Task (Final DoW)
Objectives: Define and deliver training contents about common federated services for supporting scientific activities of TSs, CCs and research communities (T11.4), and domain-specific training for data providers and data scientists (T11.5)
Descriptions: Training content (VMs/containers/slides/guides) and events
  By CCs, e.g.:
    ELIXIR core data resources
    EISCAT Data portal
    ORFEUS-EIDA e-Infra for EIDA nodes and seismology researchers
    LOFAR data school
    Master classes about DMCC+
    ICOS Carbon Portal
    eLTER data management system
  By TS providers, e.g.:
    ENES: to organize 3 f2f workshops
    LNEC: to organize a summer school
    ESA: promote training events on the integrated services
    USE: provides trainings on PAIRQURS, Citizen Science Services, GBIF, GBIF, Digtal Knowledge Preservation Framework, Remote Monitoring, Smart Sensor
Milestones: Online Training Programme of 1/2 project year [M3/12]
Deliverables: Leads D11.2, contribute to D11.1, D11.3, D11.4, D11.5

## Slide 18: Issues To Be Clarified
ITBC#1: Contacts and PMs of each party in T11.5? Are they already the contact points of TS, CCs WPs?
ITBC#2: How to collaborate with the following activities in T11.1
  T11.1: Maintain a catalogue of training events, training materials …
  T11.1: Provide a system for deployment and configuration of training env
  T11.1: Provide surveys and feedback forms
  T11.1: (9K for training events)
ITBC#3: Deliverables: which tasks? Which format?
  D11.1: Training materials about common services and thematic Services; Oth; M12: (first year training plan) -> T11.1, T11.4, T11.5
  D11.2: Training materials about competence center services; R; M24 -> T11.5
  D11.3: Updated Training materials about common service, thematic and competence services; Oth; M34; EGI.eu -> T11.1, T11.4, T11.5
  D11.4: Second Report on training activities, infrastructure and materials; R; M24 -> T11.1, T11.4, T11.5
  D11.5: Updated training materials about common, thematic and competence services; Oth; M34 -> T11.1, T11.4, T11.5
ITBC#4: Milestones in what formats?

## Slide 19: 1st Year Trainings
Objectives:
  Completion of training plan about TSs
  Completion of first set of training contents about TSs
Main Targeting Audience:
  Structured scientific communities linked to the CCs and TSs
  Domain-specific data providers and data scientists
Time lines:
  Plan: work with T11.1, schedule of 1st year TSs, CCs trainings by M3
  First set of training contents about TSs: by M12
Training Scope:
  TSs services (9)
Formats:
  Contents (Slides/Guidance/User manuals/Recordings/VMs/Containers): each service should have, need to discuss with T11.1 which platform to use
  Depending on TSs: Webinars, F2F trainings, summer schools
    Co-organise with EOSC-Hub conferences: Apr, Nov??

## Slide 20: 2nd Year Trainings
Objectives:
  Delivery of TSs trainings
  Completion of training contents of CCs
Main Targeting Audience:
  Structured scientific communities linked to the CCs and TSs
  Domain-specific data providers and data scientists
Time lines:
  Plan: work with T11.1, schedule of 2nd year trainings (about TSs, CCs) by M12
  First set of Training contents about CCs: by M24
  Delivery of planned training about TSs: by M24
Formats:
  Contents of TSs (Slides/Guidance/User manuals/Recordings/VMs/Containers): updates
  Depend on TSs, CCs’ plan

## Slide 21: 3rd Year Trainings
Objectives:
  Update of TS, CCs training contents
  Delivery of TSs, CCs trainings
Main Targeting Audience:
  Domain-specific data providers and data scientists
Time lines:
  Update of training contents: by M36
  Training delivery: by M36
Formats:
  Contents (Slides/Guidance/User manuals/Recordings/VMs/Containers): updated
  Webinars and F2F trainings:
    Tracking of TSs CCs trainings activities

## Slide 22: Tools and Templates
Catalogue of training events, materials (discuss with T11.1)
  Internal use
  Public use, e.g., towards a sustainable e-learning platform
Training material template
  For wiki
  For slides
  For user manual/guidance
  For video
Training record template (plan, preparation, delivery, evaluation)
Training feedback form (discuss with T11.1)
Training event page
Training advertising channels (WP7, 8, 9, communication team)
Users database and training mailing list
Trainers database

## Slide 23
https://docs.google.com/spreadsheets/d/1vHu0T-o-sd72cVkPGOxUI0UFA2p96FtEJenqd5ZkXAU/edit?usp=sharing

## Slide 24
Questions and Comments?