## Slide 1: EOSC-hub WP9: Joint Digital Innovation Hub
EOSC-hub Kick-off, 9-12 Jan 2018, Amsterdam
Sy Holsinger, EGI Foundation
Senior Strategy and Policy Officer - WP9 Manager

## Slide 2: Work packages

## Slide 3: WP9 Objectives
Create partnerships with SMEs/industry, innovation clusters, accelerators and investors that stimulate innovation (new products, services). Provide access to funding/grants, and increase visibility. Facilitate access to e-Infrastructure resources to support pilots, prototyping, scaling-up, design, performance verification, testing, demonstration, etc.
Offer business oriented coaching to “accelerate” market uptake and exploitation results of pilots and Competence Centers. Connect with the Pan-European network of DIHs and selected regionals. Share best practices and competencies to expand the knowledge/human capital between the public and private sector. Develop long-term business relationships outside of/beyond the project.

## Slide 4: EOSC-hub Joint DIH (WP9): Tasks/Activities
WP9 Joint Digital Innovation Hub |  | 
T9.1 | Joint DIH ecosystem (Lead: EGI Foundation) | Establishing and evolving of the DIH Collaborating with other DIHs Managing the DIH platform/tool
T9.2 | Business Pilots (Lead: PSNC) | Coordinating pilots (6 initially selected in open call) Ensuring access to services and tech support Assessing and validating results Identifying additional experiments
T9.3 | Commercialization Support (Lead: F6S) | Identifying business opportunities from the pilots Supporting technology transfer process models Mentoring program towards pilots and competence centres Defining pre-commercial agreements

## Slide 5: Deliverable and Milestones
Deliverable | Lead Beneficiary | Author | Due Date (month) | Type | Dissemination Level
D9.1 Initial Business Pilots Overview & Work Plans | PSNC | Marcin Plociennik | M03 March 2018 | Report | CO
D9.2 Joint Digital Innovation Hub Intro and Strategy | EGI.eu | Sy Holsinger | M06 June 2018 | Report | PU
D9.3 Business Pilots Results | PSNC | Marcin Plociennik | M21 Sept 2019 | Report | CO
D9.4 Joint Digital Innovation Hub Final Results and Sustainability Plan | EGI.eu | Sy Holsinger | M36 Dec 2020 | Report | PU
Milestone | Lead Beneficiary | Author | Due Date (month) | Means of verification
MS37 Business Pilot Success Stories | EGI.eu | Sy Holsinger Marcin Plociennik | M24 Dec 2019 | Published Online

## Slide 6: Task and Deliverable Timelines
PM1
PM6
PM12
M18
PM24
PM30
PM36
T9.1
Joint DIH
T9.2
Business Pilots
T9.3
Commercialization Support
D9.1
1st Business Pilot Work plans
D9.2
Joint DIH Strategy
D9.3
Business Pilot Results
PM3
PM6
PM21
D9.4
Joint DIH Final Results
PM36
M9.1
Publication of Business Pilot Success Stories
PM24

## Slide 7: WP9 Relation to other WPs
DIH
WP2: Service Portfolio/Catalogue
WP3: Innov Mgmt./ Comms / Open Calls
WP13
WP8: CCs
Mentoring
Expertise
Provisioning
New services
Marketing Support
Engagement Strategy
Exploitable Services
Open Call Mgmt.
Innovation Input
WP11
Training/Material

## Slide 8: Project KPIs – WP9
KPI# | Name | Area | BT | ST
KPI03 | Services/technologies increased in TRL via the DIH | T | 7 | 10
KPI04 | Published business pilot success stories | SE | 5 | 8
KPI05 | Signed (pre-)commercial agreements for EOSC-hub services from DIH | SE | 3 | 6
O = operational, T = technical, SE = socio-economic
BT = base target, ST = stretch target

## Slide 9: WP9 Training and Needs
Initial focus on 6 business pilots
  One-to-one consultancy/support
  Understand the ”service heat map”
Wider Digital Innovation Hub Promotion
  Individual service demos/online material (for them)
  Webinars (from us)
WP9 business coaching available to other WPs (e.g. WP7, WP8)
Timelines
  Initial 6 pilots run up to M12-M18
  D9.2 Joint Digital Innovation Hub Intro and Strategy (M6)
  D3.1 EOSC-Hub Comm. & Stakeholder Engagement Plan (M4)
Summary
  2 types of trainings foreseen, but not until 2nd half of year

## Slide 10
EOSC-hub Kick-off Meeting, 9-12 Jan 2018, Amsterdam
Thanks! Questions?
sy.holsinger@egi.eu
@syholsinger