## Slide 1: EOSC-hub / OpenAIRE-Advance Cross-project Governance

## Slide 2: Scope collaboration
Identify common strategic goals
Consider common project management structures
Ensure strategic alignment between the two projects including but not limited to community engagement, service development, and service positioning and sustainability within the EOSC

## Slide 3: Cross-Project Common Strategic Board
Ten members: five selected by OpenAIRE-Advance project; five selected from the EOSC-hub project
Remit to:
Harmonise strategies for the positioning of the projects as building blocks of EOSC
Coordinate the liaison with RIs to get feedback on the proposed collaborative plan
Work with relevant projects (such as EOSCpilot, eInfraCentral and prospective projects as they develop from WP18-20) to contribute to the respective developing governance frameworks.
Find ways on how this strategy can align with national level (liaise with e-IRG and other initiatives, e.g., GO-FAIR).
Steer and approve joint activities as proposed from Task Forces B (Communication, engagement, training) and C (Services) and other topics that are of common interest to both projects.
Will meet every 6 months starting at Q2 throughout the duration of the Collaboration Agreement

## Slide 4: Collaboration of existing management
General Assemblies
Due to legal implication and contractual constraints of the individual projects, the General Assembly of each project will stay independent within each other project.
Executive Office/ Activity Management Board
Activities of the two respective offices will be synchronized through a close collaboration of task forces B (Communication, engagement, training) and C (Services). Key operations will be aligned and transferred to respective project bodies and activities. Chairs of OpenAire-Advance and EOSC-hub projects will liaise and monitor the implementation of the approved collaboration activities and report/escalate appropriately to the OpenAire-Advance PSC/ EOSC-hub PMB.

## Slide 5: External Advisory Boards
EOSC-Hub and OpenAire-Advance will review the requirements of their advisory board, and whether there is sufficient overlap to merit a single advisory board across both projects; if there is not sufficient overlap, then the projects will consider common members between the advisory board.
This review of overlapping requirements may take into account the needs of EOSCPilot and eInfraCentral.

## Slide 6: Governance Activity Plan
Cross-Project Strategic Board membership finalised (five from each project), common work plan, detailed functions and timeline (M3)
Review of Advisory Board Requirements and setup of advisory board(s) based on this analysis (M6)
White paper outlining common vision for EOSC, service placement, and role in upcoming EOSC governance (M9)
Aligned roadmap(s) for service positioning and sustainability within EOSC (M18)
Impact on Research: cohesive alignment and strategy of key components of the EOSC Services and European Research Support Landscape