## Slide 1: EOSC-hub / OpenAIRE Collaboration
Tiziana Ferrari/EOSC-hub Project Coordinator
General Assembly meeting 1, 09 January 2018

## Slide 2: Introduction
EOSC-hub and OpenAIRE-Advance are complementary grants under EINFRA-12
“‘Complementary grants’ are different EU grants which are linked by the work programme/calls by identifying them as complementary actions.
The beneficiaries and those of the complementary grants must cooperate and provide access to their results.
They must conclude a written collaboration agreement regarding the coordination of the complementary grants and the work of the action
Annotated Model Grant Agreement: V4.1 – 26.10.2017

## Slide 3: Outline
Report on status of Collaboration Agreement and next steps
Cross-project governance
Joint work plan
  Joint Activity 1. “Service Integration”
  Joint Activity 2. “Communication, Engagement, Support and Training”
  Joint Activity 3. “Governance”

## Slide 4: Progress report
Aug-Nov
3 task forces formed
  Governance and sustainability
  Outreach, Support, Training and Communications
  Integrated service provision
Analysis for each area of:
  common stakeholders
  opportunities for collaboration
  gaps and overlaps
Dec
First draft of joint work plan (joint activities of complementary grants, outputs and timeline)

## Slide 5: Plan
Jan
Written feedback about Joint Activity Plan Draft 1 from External Board of the EC expected
10 Jan: revision of Draft 1 joint work plan  feedback to OpenAIRE about revised joint work plan
Preparation of Collaboration Agreement articles
Feb. Joint work plan Draft 2 for internal/external revision by the External Board. Includes
  Revised communication plan
  Overview of RDA of relevant working groups (participated or providing input to EOSC-hub)
March
  Written feedback from the External Board
  RDA Plenary/Berlin: Joint BoF at RDA Plenary: EOSC-hub, FREYA and OpenAIRE-Advance + 23 March: possibility of co-located event
  End of March: final Collaboration Agreement

## Slide 6: Agenda
Report from TEAM1 - Cross-project governance / Y. Legre
Report from TEAM2 - Engagement, support, training and technical support / G. Sipos
Report from TEAM3 - Service technical integration / M. v. Sanden
Discussion and prioritization of tasks with a focus on TEAM3