## Slide 1
Current status and next steps
WP7

## Slide 2
Which work you have done so far in the project:
  did you perform some kind of analysis about EOSC-hub services? Or just your community services? Is it available as a document, table, presentation?
  which community services you have improved and in which way:
    defined new algorithms? Added new components? Supported new protocols?
  which EGI/EUDAT/Indigo services you have used so far, if any, and how.
  which issues you have found and, if you have solved them, how you have done it:
    are you missing technical support to integrate some service/component? Accounting? Authentication?
    are you missing hardware resources to deploy your service?
Where are we?

## Slide 3
 | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
T7.1 |  |  |  |  | EH res |  |  |  |  |  |  | 
T7.2 |  |  |  |  |  |  |  |  |  |  |  | 
T7.3 |  |  |  |  |  | EH res |  |  |  |  |  | 
T7.4 |  |  |  | 1 |  |  |  |  |  |  |  | 
T7.5 |  |  |  |  |  |  |  |  |  |  |  | 
T7.6 |  |  |  |  |  |  |  |  |  |  |  | 
T7.7 |  |  |  | 2 |  |  |  |  |  |  |  | 
T7.8 |  |  |  |  |  |  |  |  |  |  |  | 
T7.9 |  |  |  | 1 |  |  |  |  |  |  |  | 
Where we are
WP13
T7.1
T7.2
T7.5
T7.6
T7.7
T7.8
T7.9

## Slide 4
T7.2: missing accounting technical specification
T7.4: missing resources
T7.7: missing resources
T7.9: missing information from partners
Why we are where we are

## Slide 5
Claudio Cacciari c.cacciari@cineca.it