## Slide 1
WeNMR report
12th of February 2019
Dissemination level: Public

## Slide 2: Integration with Access Enabling Services
Access Enabling services: AAI, monitoring, accounting, etc.
JIRA ticket ID | Service | Integration status (done, ongoing, planned, assessment) | Comments and Issues
https://jira.eosc-hub.eu/browse/EOSCWP10-33 | AAI | Done | 

## Slide 3: Integration with Common Services
Common services: EGI FedCloud, EUDAT B2FIND, INDIGO PaaS. etc.
JIRA ticket ID | Service | Integration status (done, ongoing, planned, assessment) | Comments and Issues
https://jira.eosc-hub.eu/browse/EOSCWP10-29 | DIRAC4EGI | Ongoing | Cloud submission tests were successful, to be released in prod by end of February
https://jira.eosc-hub.eu/browse/EOSCWP10-31 | West-Life Virtual Folder VM + B2DROP | Done | Discussions/concerns about future support of Virtual Folders.
https://jira.eosc-hub.eu/browse/EOSCWP10-32 | West-Life Virtual Folder VM + Onedata | Ongoing | A PR for Onedata support is waiting: https://github.com/h2020-westlife-eu/virtualfolder/pull/84 Status uncertain
https://jira.eosc-hub.eu/browse/EOSCWP10-30 | West-Life Virutal Folder VM + EGI FedCloud | Ongoing | Assessing support of Virtual Folders. Hardware requirements where collected, need to look for providers.

## Slide 4: Status, main achievements and issues
DIRAC was integrated with relevant portals for grid jobs, and cloud usage is being finalized
Virtual Folder integration with B2DROP was finalized
Virtual Folder PR for Onedata integration is pending
  Status unclear (compatibility among versions and potential move to WebDAV)
Virtual Folder support is unclear
  EOSC Life may support it
Need for resources providers willing to host the VM
  What to do if Virtual Folder code isn’t supported anymore?

## Slide 5: Next steps
Dirac submission to EOSC cloud resources to be deployed as a production service
Clarify status of support of Virtual Folder code
Finalize integration with Onedata
Find a provider willing to support the VM
Agree on the VM operation