## Slide 1
Dissemination level: Public
WP9 - EOSC Digital Innovation Hub (EOSC DIH)
Sy Holsinger (EGI Foundation), WP9 Manager
Luxembourg, 8-9 October 2019
Bringing Industry into the European Open Science Cloud

## Slide 2: Content Outline
Background to Digital Innovation Hubs (DIH)
EOSC DIH Intro and WP9 Structure
WP9 Activities and Results
  Strategy, Communication and Dissemination
  Business Pilots
  Commercialization support
Use of Resources
Deviations and Lessons Learned
Future Plans and Conclusions
2
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 3: EC Digital Innovation Hub Initiative
Background and landscape
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
3

## Slide 4
Digital Innovation Hub
EC definition
What is a Digital Innovation Hub?
  An ecosystem of start-ups, SMEs, large industries, researchers, accelerators and investors that fosters the creation of partnerships to stimulate innovation.
4
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 5
EOSC identified as a key component
Created the EOSC DIH
5
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 6: DIH Service Needs
*Andrea Halmos, European Commission, DG CONNECT, Unit A2, Technologies & Systems for Digitising Industry
6
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 7: European Landscape of DIHs
Agile, and demand-driven, Digital Innovation Hubs in Europe are sustainable innovation ecosystems, not just a gateway to services.
€110m of funding has been invested in I4MS since 2013; - 11 large projects funded by FP7 and H2020, 70 competence centres;
22 innovation hubs all over the European continent, soon expanding worldwide
Digital Innovation Hubs in H2020: The EC is focusing EUR 300M in H2020 (2018-2020) – short time from idea to hands-on experimentation and development.
7
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 8: Digital Innovation Hubs Catalogue
First version available:
Fact-sheets with profile, contact data, service examples for regional, national, and EU- supported DIHs
Map-based search tool by technical competences, market sector, services
http://s3platform.jrc.ec.europa.eu/digital-innovation-hubs-tool
8
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 9: EC DIH Support
Derive recommendations to the High-Level Governance; Build DIH Community
WG on Digital Innovation Hubs
2. Joint WG of DEI and Multi Stakeholder Platform (MSP) on standardization activities of Digital Industrial Platforms
3. WG on Future Partnerships
3 Working Groups
DIHnet Project
9
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 10: Role of Industry in the EOSC
Procurement
Participate in the procurement framework (see WP12)
Customer
Making use of existing EOSC services
Provider
Offering services to EOSC
Partner
Co-development
10
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 11: EOSC Digital Innovation Hub
WP9 structure
11
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 12: Key Exploitable Results WP9
Service Providers:
Provide services for
Researchers
Enterprise: Develop, expose and grow my services
Researchers and
research communities:
Empower my research
EOSC Hub Operators: Develop the EOSC landscape
Educate, inform and support my team and community
Training courses and materials
EOSC Portal
and
Marketplace
Services in the EOSC Service Portfolio
Digital Innovation Hub:
platform for industrial collaborations with EOSC
Rules of Participation
Service Management System
Interoperability & Integration Guidelines
Internal services in the Hub portfolio
Business and sustainability models for services and the Hub
12
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 13
Builds on the EC initiative to onboard industrial partnerships within the EOSC
Joint effort from years of individual e-Infrastructure industry engagement programs
Focused on (not limited to) start-ups and SMEs
Starts with 6 business pilots selected during project preparation; open for many more
To persist beyond the life of any support project (e.g. EOSC-hub project – www.eosc-hub.eu)
Driven by
13
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 14: EOSC DIH: Objectives
Offer access to e-Infrastructure resources to support pilots, prototyping, scaling-up, design, performance verification, testing, demonstration, etc.
Facilitate partnerships with SMEs/industry, innovation clusters, accelerators and investors that stimulate innovation
Increase visibility on a European/International level
Provide business coaching and training to “accelerate” market uptake and exploitation results
Support access to funding/grants
Develop long-term business relationships
14
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 15: EOSC DIH: Services
Pilots/proofs of concepts
Service/Product design
PaaS/SaaS Integration
Performance verification
Testing
Piloting and co-design
Technical consultancy
Service management
Commercialization and business coaching
Brokerage to funding and opportunities
Training & Support
Compute (HTC, HPC, Cloud)
Storage (Online/Archive)
Data management
Research data
Tools & applications
Technical access
Media Exposure
Participation to events
Promotional print material
Inclusion in marketplace
Networking
Visibility
15
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 16: EOSC DIH: WP9 Task, Activities and KPIs
T9.1 | Joint DIH ecosystem (Lead: EGI Foundation) | Establish and evolve the DIH Communicate and disseminate the DIH Collaborate with other DIHs Manage the DIH platform/tool
T9.2 | Business Pilots (Lead: PSNC) | Coordinate pilots (6 initially selected in open call) Ensure access to services and tech support Assess and validate results Identify additional pilots
T9.3 | Commercialization Support (Lead: F6S) | Identify business opportunities from the pilots Support technology transfer process models Mentor pilots and competence centres Define pre-commercial agreements
KPI# | Name | Area | BT | ST
KPI03 | Services/technologies increased in TRL via the DIH | T | 7 | 10
KPI04 | Published business pilot success stories | SE | 5 | 8
KPI05 | Signed (pre-)commercial agreements for EOSC-hub services from DIH | SE | 3 | 6
16
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 17: EOSC DIH: WP9 Timelines
PM1
PM6
PM12
M18
PM24
PM30
PM36
T9.1
Joint DIH
T9.2
Business Pilots
T9.3
Commercialization Support
D9.1
1st Business Pilot Work plans
D9.2
Joint DIH Strategy
D9.3
Business Pilot Results
PM3
PM6
PM21
D9.4
Joint DIH Final Results
PM36
M9.1
Publication of Business Pilot Success Stories
PM24
Delivered
17
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 18: WP9 Activities and Results
Strategy, Communication and Dissemination
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
18

## Slide 19: Strategy and Promotion
Strategy
  “EOSC DIH”, as the mechanism for industry to engage the EOSC; live beyond the life of the project
  D9.2 "Joint Digital Innovation Hub Intro and Strategy" (M6 – Jun)
  Official DIH registered in EC Catalogue
Promotional Material
  Dedicated DIH logos and URL
  EOSC-hub website: Dedicated DIH page content
  Video interviews: DIH intro + ICT 2018 promo video
  EOSC-hub Magazine: DIH article (issue 1)
  Usable slide decks, brochure, poster, banner
  Twitter account = 90+ tweets; 300+ followers
19
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 20: Events Organized and Attended
20
Organized
  DI4R 2018 (Lisbon – Oct’18): “DIHs for Industry Engagement” Session
  ICT 2018 (Vienna – Dec’18): Networking session; Joint DIH Booth participation
  CompBioMed Webinar (May ‘19): “Open data services for biomedicine business”
  EOSC-hub Week (Prague – Apr’19): “SME/industry engagement within EOSC”
  7th IT Future Expo (Warsaw – Sept’19): Exhibition Booth (3000+ attendees)
Presented
  ICTFOOTPRINT.eu Workshop “Green ICT” (Amsterdam – Mar’18)
  ELIXIR Innovation and SME Forum (Frankfurt – Oct’18)
  EC DIH Working Group Meetings (Brussels - Apr,’19)
  SmartAgriHubs North East Europe Workshop (Poznan – May’19)
  BDVA PPP Summit (Riga – Jun ’19)
  EC JRC / Net Service F2F (Bologna – Jul’19)
Attended
  EC DIH Working Group Meetings (Feb, May, Jul ‘18; Brussels - Apr, Jul’19)
  BDVA Group Meetings (Brussels - Mar, Apr, Jun, Sep’18) + Meetup (Sofia – May ‘18)
  EC DIH Annual Event (Warsaw – Nov’18)
  Several local industry events in Poland (May, Jun’19)
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 21: Industry Collaborations
Various Stages of Development
21
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
Finalizing Pilot
Under Discussion
Projects
Networks & DIHs
Partners & Providers
Other

## Slide 22: Vouchers, Marketplace, Platform
Vouchers
Collaboration Platform
*prototype based on
EOSC Marketplace
*additional options based on use case
22
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 23: WP9 Activities and Results
Initial 6 pre-selected business pilots + additional ones onboarded
23
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 24
Our Initial 6 Business Pilots
ACTION Seaport
Space Weather Data for the DRACO Observatory
Bot Mitigation Engine
Sport Smart Video Analysis
CyberHAB
Furniture Enterprise Analytics Datafurn
24
24
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 25
ACTION Seaport
Space Weather Data for the DRACO Observatory
Bot Mitigation Engine
Sport Smart Video Analysis
CyberHAB
Furniture Enterprise Analytics Datafurn
Improving safety and operational performance of seaports
A Cloud Framework for State-of-the-art Space Weather
Using data cloud services to manage harmful algae blooms
Solutions to secure online services from Botnets Attacks
Analyzing Sport Performance through a Cloud-hosted platform
Platform-as-a-Service Data Analytics for the Furniture Industry
25
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
Our Initial 6 Business Pilots

## Slide 26
ACTION Seaport
Space Weather Data for the DRACO Observatory
Bot Mitigation Engine
Sport Smart Video Analysis
CyberHAB
Furniture Enterprise Analytics Datafurn
TRL 7->8
TRL 4->7
TRL 5->7
TRL 2->7
TRL 4->7
TRL 5->8
SME->Large Enterprise
Acquired
26
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
Our Initial 6 Business Pilots

## Slide 27
Deliverables / Milestones
  D9.1 and D9.3 provided on time
  Success stories publication (anticipated from PM24)
Pilots implementation
  Each pilot followed detailed implementation plan (D9.1):
    Plans, design, architecture, early demonstrators, release for early adopters, final pilot release, dissemination and exploitation
Direct support
  Status meetings: 3-weekly meetings
  Technical one-to-one meetings with pilots
  Arranged meetings with experts for given tech
  Analysis of business pilots from different perspectives
  Communication between pilots and WP1, WP3, WP10
Important Events
  DI4R 2018 (Lisbon – Oct’18): Preparations and presentation of 2 demos
  EOSC Week in Prague: Preparation and presentation of 4 remaining ones (best demo prize for one of the pilot among 14 competitors)
27
Business Pilots Support
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 28: Business Pilots: Services/Resources Used
# | Pilot | Type of infrastructure | EOSC sites | EOSC services used | TRL increased
1 | CyberHAB | Cloud infrastructure (OpenStack) VM has: 20CPUs, 256GB of memory, 50GB of disk and a 500GB volume, 50GB in OneData | IFCA (ES) | Jupyter Notebook, Cloud Compute; Onedata (EGI DataHub); INDIGO IAM | 5 -> 7
2 | Sports Smart Video Analysis | Cloud infrastructure (OpenStack) VM: 4 cores 16GB RAM (frontend) + instance g3.large 12 vCPU, 22GB RAM, 1x 1080Ti (computing) + 100GB storage | IFCA (ES) | Cloud Compute | 4 -> 7
3 | ACTION Seaport | OpenStack 20 CPU, 40 GB ram, 1080 GB data | PSNC (PL) | Cloud Compute | 7 -> 8
4 | Guardomic | OpenStack 18 CPU, 34 GB RAM, 1670 GB data | PSNC (PL) | Cloud Compute | 2 -> 7
5 | DRACO Observatory | Virtual machine with 2 virtual CPUs and 16GB of RAM. Root storage of 8GB | CESGA (ES) | Cloud Compute | 4 -> 6
6 | Furniture Enterprise Analytics | Cloud Compute (80 vCPUs and 160 GBs RAM) | INFN-Bari (IT) | Cloud Compute | 5 -> 8
28
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 29
EOSC DIH: Success Stories Publication
29
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 30
2 New Business Pilots Onboarded
Artificial Intelligence for rare disease diagnosis
Blockchain for university certificates
30
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
“Coming soon”
Video coding and compression

## Slide 31: Commercialization Support
Webinars and pilot consultancy
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019
31

## Slide 32: Commercialization Support
Planning
  Contributions to D9.1, D3.1 and D9.3
Webinars/Events
  DI4R 2018 (Lisbon – Oct’18): Presented Commercialization support service offer
  Survey ran to find the topics of most interest
  “How to Pitch” webinar via ESIL project (Nov’18)
  “Business internationalization” Webinar ran (Jun’19)
Direct support
  Business Pilots: Attendance of regular meetings
  WP7: task leader meeting attendance
  Analysis of business pilot final report to start defining pre-commercial agreements (3 of 6).
Most activities will take place in 2nd half of project (by design)
32
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 33: Commercialization Support
Connecting to related European DIH’s
  Trinity DIH: foster EU competitiveness through digitization https://projects.tuni.fi/trinity/
  Diatomic Project: a network of digital innovation hubs in Advanced Robotics https://diatomic.eu/
F6S Platform
  Set up pages for EOSC DIH for the startup community
  Main page: https://www.f6s.com/eosc-hub
  EOSC DIH: https://www.f6s.com/eoscdigitalinnovationhub
  EOSC Free trial: https://www.f6s.com/eoscdihfreetrial.
Most activities will take place in 2nd half of project (by design)
33
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 34: Use of Resources
Project effort and technical support
34
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 35: WP9: PM Plan and Consumption
Overall effort consumed in line with project activities and plans (no major impact)
T9.3 to ramp in second half of project by design
WP | Task No. | Task Name | P1 M1 - M18 |  | 
 |  |  | Planned PM | Used PM | Used%
WP09 | T09.01 | Joint DIH Ecosystem | 17.5 | 15.8 | 90%
 | T09.02 | Business Pilots | 152.4 | 133.3 | 87%
 |  | Unfunded effort | 6.3 | 7.4 | 118%
 | T09.03 | Commercialization Support | 13.8 | 5.3 | 39%
WP09 Total |  |  | 190 | 161.8 | 85%
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 36: WP9: Budget for Technical Resources
€100,000 allocated to WP9 for supporting pilots with additional resources as needed and to support the onboarding of new pilots
No cascade funding mechanism available
PMs available only to project consortium members
Total budget for Infrastructure | €100,000
Budget Allocated | €30,050
Budget Remaining | €69,950
Avg. cost per use case to date | €5,510
Est. Use Cases Remaining | 12
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 37: Deviations / Lessons Learned
WP Admin
  Change of business pilot partner: Action Modulers -> Bentley
    Was managed, but took quite a bit of time/effort
  Some staffing issues within project partners
    UCL: plans to ramp effort within 2nd half of project
    CINECA: EGI supported one pilot not foreseen; discussing shift of leadership of onboarding new pilots to PSNC
      Only for personnel effort, technical resources to support pilots is still foreseen
  Allocated budget of €100k during project
    Positive, but the need had to be defined then managed
Business Pilots
  Communication between pilots and project members
    Terminology around project related aspects was new and not always understood
    Many things needed to be repeated several times or clarified
  Need to streamline and improve onboarding process
  Some availability/reliability issues with resources, but has pushed to improve the way services are delivered
37
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 38: Future plans
Joint DIH Ecosystem
  Continue the momentum generated in first half of project; DIHs are now becoming known
  Extend the EOSC DIH service offer and refine promotional material
  Need to add EOSC DIH information to the EOSC Portal
  Disseminate and communicate through event organisation and participation as well as social media
  Finalize collaborations and reach out to new contacts including other DIHs around Europe; Many requests coming in
  Further develop online platform to coalesce a community of industry participants, experts, innovators, and funding bodies
  Investigate sustainability models post-project (i.e. multi-partner legal entities or collaborations)
Business Pilots
  Provide support to ensure intended results are achieved and potential long-term agreements analyzed
  Onboard new pilots, which is not only a project KPI, but an important activity for the long-term viability of the EOSC DIH
  Expand the industry voucher programme to continuously entice new industry customers
Commercialisation Support
  Support the business pilots and establish pre-commercial agreements
  Ramp up webinars and one-to-one consultancy sessions with pilots, competence centers and thematic service providers
  Connect with accelerators and funders
38
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 39
Summary
8
Business Pilots
169
VMs Instantiated
6
Success Stories
18
Industry Events
4
Services in EOSC MP
€500k
Direct SME Support
319
Twitter Followers
442k
CPU
Hours
EOSC DIH in Numbers
39
09/10/2019
WP9 EOSC DIH - 1st EOSC-hub Review, Luxembourg 8-9 Oct 2019

## Slide 40
EOSC DIH Team
Sy Holsinger (EGI)
Elisa Cauhe (EGI)
Marcin Plociennik (PSNC)
Agnieszka Rabenda-Tomczak (PSNC)
Konrad Leszczynski (PSNC)
Claudio Arlandini (CINECA)
Giuseppe Fiameni (CINECA)
Nuno Varandas (F6S)
Hugo Cantão (F6S)
Catherine O'Donoghue (F6S)
David Wright (UCL)
EOSC DIH Partners