## Slide 1: EGI-InSPIRE SA3: Heavy User Communities Milestones & Deliverables
Jamie Shiers, CERN
EGI-InSPIRE SA3 Wiki

## Slide 2: Timetable (1/3)
Month | What | Description
1 | MS601 | HUC Contact points and the support model (CSC)
3 | QR | Quarterly Report
4 | MS602 | HUC Software Roadmap (INFN)
4 | MS603 | Services for High Energy Physics (HEP)
4 | MS604 | Services for the Life Science Community (CNRS)
4 | D6.1 | Capabilities offered by the HUCs to other communities
6 | QR | Quarterly report
8 | MS605 | Training and dissemination event with EGI UF (TCD)
9 | D6.2 | Sustainability plans for the HUC activities
9 | QR | Quarterly report
10 | MS606 | HUC Software Roadmap (INFN)
11 | D6.3 | Annual Report on the HUC Tools and Services
12 | QR | Quarterly report
12 | MS607 | Hydra service deployment on a multi-servers configuration (CNRS)
12 | MS608 | Integration of the VisIVO server with the production infrastructure (INFN)

## Slide 3: Timetable (2/3)
Month | What | Description
13 | MS609 | HUC Contact points and the support model
15 | QR | Quarterly Report
15 | MS610 | HUC Software Roadmap
15 | MS603 | Services for High Energy Physics
15 | MS611 | Services for the Life Science Community
16 | D6.4 | Capabilities offered by the HUCs to other communities
16 | MS612 | HUC Software Roadmap
18 | QR | Quarterly report
20 | MS613 | Training and dissemination event with EGI UF
21 | D6.5 | Sustainability plans for the HUC activities
21 | QR | Quarterly report
22 | MS612 | HUC Software Roadmap
23 | D6.6 | Annual Report on the HUC Tools and Services
24 | QR | Quarterly report

## Slide 4: Timetable (3/3)
Month | What | Description
25 | MS615 | HUC Software Roadmap
27 | MS616 | Services for HEP
27 | QR | Quarterly Report
27 | D6.7 | Capabilities offered by the HUCs to other communities
27 | MS617 | Services for the Life Science Community
28 | MS618 | HUC Software Roadmap
30 | QR | Quarterly report
32 | MS619 | Training and dissemination event with EGI UF
33 | D6.8 | Sustainability plans for the HUC activities
33 | QR | Quarterly report
35 | D6.9 | Annual Report on the HUC Tools and Services
36 | QR | Quarterly report
36 | MS620 | HUC Software Roadmap