## Slide 1
David Kelsey (STFC - UK Research and Innovation) EOSC-hub Task 4.4 meeting – 11 Sep 2020
Task 4.4 – virtual meeting
Dissemination level: Public

## Slide 2
Just 4 months left (out of 36)
What do we work on during this time?
  Concentrate on that which will be useful for the future project(s) in 2021
  Sustainability in new “EOSC-Future”
    Or elsewhere in WISE, AEGIS
  Also: useful for our individual Infrastructures (EGI, WLCG, EUDAT …)
Today
  Look at some more of our future plans and prioritise etc.
Note that many of the sub-tasks have already reported and been discussed yesterday (IRTF, SVG, SSC, SOC, monitoring, …)
EOSC-hub Task 4.4 discussion

## Slide 3
Results of July 2020 audit of EOSC-hub SMS
  How will we respond?
Work on security risk assessments
  Complete work on the Marketplace assessment
  Do more assessments
    We said “two more” – what do we include?
Work on a procedure for handling security controls
Do we volunteer to join another SMS audit before the end of the year?
Review/update other procedures?
Policy work
Topics to discuss today

## Slide 4
Risk assessment team – Urpo, Linda, DaveK
Work completed (3rd July 2020) and written up
  Report sent to senior management
Scope of assessment
We are primarily assessing the security risk associated with the strategy for on-boarding services
https://wiki.eosc-hub.eu/display/EOSC/SPM1+Add+a+service+in+the+EOSC+Service+Portfolio
to ensure that users can trust the services in the catalogue. Additionally, we are considering the risk posed by other threats related to the marketplace and catalogue.
However this is NOT a risk assessment of the services themselves.
Meeting scheduled for 23 Sep 2020 to discuss with all stakeholders
Review the report today?
Risk assessment of EOSC Marketplace

## Slide 5
A 1-hour session (75 minutes allowed – finished early)
happy with progress made (they enjoyed the EOSC Marketplace Incident and the risk assessment)
pleased to see that we had addressed the two strong recommendations from last year
The ISM5 procedure (Risk Management) is great they say for describing how to do the Risk Assessment
But it needs expanding to include full handling/management of risks and checking deployment of controls.
I told them how we will do it – they said fine – but they want some rows added to the procedure steps addressing this (will be a Strong Recommendation).
It actually ended up being a “NON-CONFORMITY”
  Needs definition and assignment of risk treatment measures
  Tracking of their implementation
  Review of their success/effectiveness
BUT we also got a “positive aspect mark”- just one of 4 in the whole SMS
  in recognition of the risk assessment procedure we have developed and are using
Audit of ISM process

## Slide 6
Show two slides from the audit report session
EOSC-hub SMS audit (first week of July 2020)

## Slide 7
All will be done in collaboration with WISE and GN4-3 EnCo team
  Also taking into account what could be useful for EOSC Future
Use experience from UK IRIS infrastructure on developing new polices based on the AARC PDK and produce new templates for the WISE PDK
  Service Operations
  Community policy?
  Top-level template
New guidance for maturity assessment versus SCI version 2
Policy work

## Slide 8
https://confluence.egi.eu/display/EOSC/ISM+Jira+Actions
EOSCSMST-nnn
  316 finalise ISM security controls and risk
  317 security risk assessment for Hub Services (ask SVB to define 2)
  318 all procedures and policies to be “approved”
  319 handover documentation for EOSC Future
  320 clarify presentation of KPIs
EOSCIS-15 define security contact for EOSC branded services
  Abuse at eosc-portal.eu created (and Matthew V has management of this)
  Is this enough?
EOSC-hub ISM actions

## Slide 9
Do we volunteer for another SMS audit?
  They will want to see risks and controls
  And more evidence of “using” the procedures
Input from other tasks/people?
Other sub-tasks – or plans of individuals

## Slide 10
Thank you for your attention
Questions?
David.Kelsey@STFC.ac.uk
Contact