## Slide 1: EAP App 8: Mapping the sensitivity of mitigation scenarios to societal choices
Bas van Ruijven, Alessandro Costantini
Meeting 07/10/2020

## Slide 2: Usecase and EOSC-hub Services
PI
  Bas van Ruijven (IIASA, Austria, vruijven@iiasa.ac.at)
Objective
  Perform modeling studies to explore how future energy systems can evolve and to quantify the tradeoffs, co-benefits, and interlinkages between different aspects of the global energy systems in the context of international climate change policy and sustainable development.
Use case
  The IAM MESSAGEix-GLOBIOM (considered by the applicants at TRL9) will run sequentially on the selected resources where each job is independent from the other in a parametric fashion.
Resources
  EOSC Federated Authentication mechanism -> EGI Chech-in
  EGI Cloud Compute service -> Provider INFN-Bari
  Storage service -> Provider INFN-Bari
SLA
  Cloud Compute: Number of virtual CPU cores: 200 / Memory per core (GB): 44 / Local disk (GB): 6144 (in total)
  Online Storage: Guaranteed storage capacity [TB]: 6 / Standard interfaces supported: POSIX, SWIFT1 / Storage technology: CEPH, with block storage exposed via POSIX

## Slide 3: Activities carried out by IIASA
First effort made to understand the various pieces (authentication, registration, VPN, tooling, etc.) needed to access the cloud resources.
  writing a guide understandable by less experienced people
Activity ongoing to introduce changes to the model code that are necessary to automate job creation/execution/reporting
Working on the initial demo
  Run few jobs implementing the mentioned changes and automation
  Became a project milestones.
GITHUB repo created
  To track activities and speed-up communications

## Slide 4: Project Status
Workplan and related roadmap were still valid, but shifted by 3 months
  https://docs.google.com/document/d/1edYX1cF1B7bFN1d4HcbG7Sa-KKV8HpRk/edit
Currently key-personnel issues
  Software engineer moved to new position
  Main modeler has to focus on other projects
  Hiring new software engineer and moving project to another group, but

## Slide 5: EAP Internal Status
Status of the technical plan
  https://docs.google.com/document/d/1edYX1cF1B7bFN1d4HcbG7Sa-KKV8HpRk/edit
  VO Created -> vo.iiasa.ac.at
  Resources to be added
Status of your project in the Community Requirement database
  Created, working on it
  https://wiki.eosc-hub.eu/display/EOSC/Community+requirements+DB
Status of your project in the EOSC Marketplace
  Created, working on it
Status of your project in the T8.9
- Created, working on it - https://wiki.eosc-hub.eu/display/EOSC/Mapping+the+sensitivity+of+mitigation+scenarios+to+societal+choices+pilot