## Slide 1
EGI-ACE Open Call no.4
Checkpoint meeting with Shepherds
Andrea Manzi/EGI Foundation
Towards an e-infrastructure for plant phenotyping

## Slide 2: Outline
Background about the scientific use case
Ambition, Impact and Challenges
Capacity Requirements
Timeline
Current status
Dissemination

## Slide 3: Background about the scientific use case
Application submitted by the partners EMPHASIS
(European Infrastructure for Multi-scale Plant Phenomics and Simulation) infrastructure.
Beneficiaries of the use case will be :
  Researchers using the phenotyping platforms at UCPH, UHEL and other universities participating in the NordPlant hub (a climate and plant phenomics university hub for sustainable agriculture and forest production in future Nordic climates);
  researchers from the French plant phenomic Infrastructure PHENOME- EMPHASIS;
  the Netherlands Plant Eco-phenotyping Centre (NPEC) which is a joint initiative of Wageningen University & Research and Utrecht University.

## Slide 4: Ambition, Impact, Challenge(s)
Scientific objectives:
analyze raw data (thousand of images) and extract variables of agronomic interest;
combine data coming from several sources including large genetic and environmental
variabilities and run meta analysis in order to predict the response of genotypes and
species to current and future climate scenarios;
structure the data (raw and processed data) in a way that it can be shared and
reanalyzed by a wide scientific community: using a standardized, unique and
unambiguous identification of objects involved in experiments, enriching datasets with
knowledge and metadata enabling the reuse of data and meta-analyses;
evaluate online deep learning and iterate with shared annotation and training/testing.

## Slide 5: Capacity Requirements
Requested EGI-ACE services :
Authentication service : EGI Check-In service.
Cloud services : EGI Cloud compute (including GPU-enabled instances).
Storage service : EGI Datahub
AI/ML services : DEEP-PaaS
Capacity:
PHIS information system : vCPU, 32Go vRAM, 100Gb disk per instance (3 instances)
Cytomine : 16 VCPUS, 32GB RAM, 80GB disk
RootPainter software : one instance with at least a GPU, 1TB for data storage.
EGI DataHub :10TB distributed storage

## Slide 6: Timeline
16 month duration ( till the end of EGI -ACE)
Month 1-4: deploy the basic components of the e-infrastructure
  Task 1 : provisioning services
  Task 2: deploy the instances of the PHIS information system on the EGI infrastructure and connect it with EGI services (EGI check-In, EGI DataHub)
  Task 3: deploy a basic computing environment (Cytomine, rootpainter) and connect it with GPU resources.
Month 5-8: customize e-infrastructure components, testing
  Task 4 : deploy an interactive environment to annotate datasets.
  Task 5 : develop analysis workflows.
  Task 6 : connect information system to meta portals using the communication layer.
  Task 7 : connect the information system to a publishing portal (DataVerse).
  Task 8 : benchmark between distributed data storage service (IRODS and OneData).

## Slide 7: Timeline
Month 9-12: make a proof of concept on identified use cases
  Task 9 : upload data to the PHIS information system.
  Task 10 : identified public datasets.
  Task 11 : harvest metadata into meta portals.
  Task 12 : annotate the training datasets and run analysis workflows on the e-infrastructure.
Month 13-16 : training, improvements and reporting
  Task 13: train user community, increase training datasets.
  Task 14 : improve AI-tools based on user feedbacks.
  Task 15: reporting.
EOSC Marketplace publication to be discussed.

## Slide 8: First Activities - Months 1-4
EMPHASIS was one of the EOSC-Hub Early adopter, so we didn’t start from scratch
Monthly meetings running since January to discuss the new requirements and status of the activities
VO already available based on Comanage ( vo.emphasisproject.eu)
CESNET cloud resources reused and extended to include also GPU access
  56 CPUs
  228 GB RAM
  Node with GPU
Existing OLA/SLA still under update ( IN2P3-IRES on the SLA, should be removed)

## Slide 9: First Activities - Months 1-4
Dedicated EGI DataHub Oneprovider already available at CESNET (10TB space)
Configuration of VMOps for the vo.emphasisproject.eu done
Various meeting to present and discuss the usage of DEEP-PaaS
  Access granted to some members of the project
  Users are creating their models and will use the service for training them
  Access to GPUs granted
  Good support from CSIC
Created orders in EOSC Marketplace

## Slide 10: Customize e-infrastructure components, testing - months 5 - 8
PHIS Instances deployed at CESNET
  3 instances deployed with a reverse proxy to access them and integration with EGI Check-in almost finalized
  Data upload already started
Created a new domain in DynDNS service: emphasis.fedcloud.eu
Storage integration
  First tests with their Nextcloud instance, then DataHub will be integrated.

## Slide 11: Wishlist
Requested EGI-ACE funding to support the installation of Cytomine software by a private company.
  Redirected to EOSC Future call for funding for Research infrastructures
Usage of a “backup as a service” solution for their VMs
  interested in testing Raksha or Freezer Openstack services
  backup now will be done using the VM Snapshot feature
Started already discussions around the usage of the services after the end of EGI-ACE project

## Slide 12: Dissemination
Abstract for a Lighting talk at EGI Conference 2022 submitted
Presentation of EGI-ACE Call for use cases (Andrea, EGI) and DEEP PaaS (Ignacio, CSIC) at a Deep Learning Training event organized by CNRS on 15/06