## Slide 1
Consultation meeting
EOSC Beyond Consortium Agreement
Tiziana Ferrari
EGI Foundation
13-12-2023
Consortium Meeting
EOSC Beyond Project Consortium Parties
TLP: AMBER Internal Use

## Slide 2: Objectives of the meeting
Subtitle
About Lump Sum Projects and related risks
Recommendations from the DESCA group
Discussion

## Slide 3
Lump Sum Projects and related risks
Definition of accepted budget in an incomplete WPs

## Slide 4: Acceptance of work packages

## Slide 5: Payment schedule

## Slide 6: Reporting and payment

## Slide 7: Ec-post controls

## Slide 8: Definition of budget – Annex 2
How to define the ‘partial amount’ of accepted budget in case of incomplete WP?

## Slide 9: Definition of budget – Annex 2 (cont)

## Slide 10: Dependencies of between deliverables
In LS projects the ability to receive in full the LS contribution of a partner in one WP depends on
  the successful completion of all results of the WP
  The successful completion of results from other WPs a given WP depends on
An under/no performing party or leaving party in one WP can affect
  The timeline of the payment of the other parties of the WP - Incomplete WPs are paid at the end of the project
  The ability to receive the full amount due - The lump sum contribution may be paid partially depending on the degree of completion of a WP

## Slide 11: Conclusions - budget
  Annex 2 does not provide sufficient information in case the cost of a WP is partly accepted
  In order to determine the amount of budget which can be accepted within an incomplete WP, is important that the consortium tracks
    For each WP, the budget allocated to each WP deliverable
    For each deliverable, the participating partners and their respective budget share

## Slide 12: Conclusions - Monitoring
It is a vested interest of all parties that costs sustained are paid in full and payments are on time
The degree of completion of a WP needs needs to be monitored
Distribution of payment should take into account progress achieved by parties in contributing to deliverables
It is in the interest of all performing parties that costs sustained are paid in full and payments are on time

## Slide 13
DESCA recommendations

## Slide 14: Recommendations from DESCA team
DESCA template for LS projects is in draft status and will not be completed in time for the start of EOSC Beyond
DESCA team recommendations
  Determine dependencies among partners of the same work package and different work packages to easily determine the distribution of liability for improper implementation
  Monitor implementation at WP and project level and determine % of partial completion of a WP, the responsible parties and their % of responsibility
  Monitor implementation at WP and project level
  Protect the consortium from risks related to recollection of undue payments
  Define mechanisms to determine liability in case of termination of a partner within a WP
  Manage timeline of payment of leaving members

## Slide 15
Reporting
DESCA Recommendations

## Slide 16: Recommendations from DESCA team
It is of increased importance to continuously monitor the progress of the implementation of the Project at the level of a Work Package Leader Group (or other equivalent Governance Structure body)
  Introduction of ‘Internal Progress Reports’ and ‘Termination Reports’
A Party leaving the consortium shall provide guidance to the other Parties on the tasks originally attributed to them to support the development of alternative solutions for the completion of work packages and a reallocation of tasks via the termination amendment.

## Slide 17: Recommendations from DESCA team - Cont

## Slide 18
Governance and monitoring
DESCA Recommendations

## Slide 19: Recommendations from DESCA team - Governance

## Slide 20: Recommendations from DESCA team - Governance
Executive board
  The EB (or equivalent group in the project governance) shall have extraordinary meetings scheduled in order to be able to decide on the individual performance of single beneficiaries in case of termination and non-completion of WPs at final reporting and amendments.
    Checking justification of deviations, if any; comparing essential planned tasks with equivalent and alternative tasks, if any; comparing the work package status with performance indicators such as deliverables and milestones;
    Reallocation suggestions for reshaping of / shifts between WPs come from the WP leaders (amendment Annex 1 of the Grant Agreement) as well as suggestions for the reallocation of budget shares (amendment of Annex 2 of the Grant Agreement) may become necessary if it appears that a WP cannot be completed as initially planned.

## Slide 21: Proposal - Extension to Section 4.2 Breach and Conflict of Interest
In case of partially funded WP or not funded WP, General Assembly identifies a breach and decides on share of responsibility of Parties and distribution of financial penalties upon proposal of the Executive Board (or equivalent body in the project governance)
  EB members may have a conflict of interest
According to current DESCA Article 12.2.4 Veto rights, ‘A Party may neither veto decisions relating to its identification to be in breach of its obligations nor to its identification as a Defaulting Party. The Defaulting Party may not veto decisions relating to its participation and termination in the consortium or the consequences of them’
  Partners involved in an incomplete WP should not be allowed to participate in decisions that concern Breach

## Slide 22: Decision making process
The Parties shall use amicable, good-faith negotiations to agree on the party or parties responsible of no/partial performance and their % of responsibility
  Failing an amicable resolution within 14 days of receipt of the relevant quarterly payment by the Lead Entity, the dispute will be referred to a Dispute Review Expert (DRE) - an expert familiar with the Project and contract interpretation, remaining impartial to all Parties.
  The DRE's decision on attributions concerning damages, liquidated damages, or price reductions will be non-binding.
  Should the Parties fail to agree on a DRE or are unsatisfied with the DRE's decision, or if the DRE doesn't decide within 40 days of the request, any Party may initiate a standard procedure for settlement of disputes

## Slide 23
Funding
DESCA Recommendations

## Slide 24: DESCA Recommendations - Funding

## Slide 25: DESCA Recommendations - Transfer of pre-financing according to installments

## Slide 26: DESCA Recommendations - Funding
Transfer of pre-financing according to installments
  The General Assembly should agree on the calculation of the excess payment amount. The excess payment amount could be set as the difference between the funding received and the interim amount approved by the Granting Authority minus a fixed percentage of the pre-financing.
  The fixed percentage should be agreed by the Parties upfront and allow for a certain but restricted float of money for work package implementation.

## Slide 27: DESCA Recommendations - Transfer of pre-financing according to installments (cont)

## Slide 28: Example of internal reporting plan and project financing plan
Reporting period 1: M1-M15
  M5: 1st internal progress report
  M10: 2nd internal progress report
  M15: 3rd internal progress report
Reporting period 2: M16-M30
  M20: 4th internal progress report
  M25: 5th internal progress report
  M30: 6th internal progress report
Mutual Insurance Mechanism: 5%
 | Internal reporting periods | 30% of pre financing | Aggregate funding received | Precondition
First reporting period M1-M15 | 1st internal period M1-M5 | 30% of total pre financing (4 M€) |  | Receipt of pre financing by EC
 | 2nd internal period M6-M10 | 15% | 45% | Upon positive performance assessment
 | 3rd internal period M11-M15 | 15% | 60% | Upon positive performance assessment
Second reporting period M16-M30 | 4th internal period M16-M20 | 15% | 75% | Upon positive performance assessment
 | 5th internal period M21-M25 | 15% | 90% | Upon receipt of 1st interim payment and positive performance assessment
 | 6th internal period M26-M30 | 5% | 95% | Upon positive performance assessment
 | Final payment | 5% | 100% | Upon acceptance of all participated WPs

## Slide 29
Monitoring
DESCA Recommendations

## Slide 30: Monitoring progress of a WP
DESCA recommends monitoring of status of completion at WP level through checking progress of deliverables and milestones and performance indicators
  The Consortium Plan and budget defined in Annex 2 currently do not provide indication of share of funding by milestone and deliverable
  The current DESCA template draft does not provide indications on how to manage this information
Proposal
  An annex to the CA is created defining for each WP
    The cost share of each deliverable/milestone - what is the cost associated to a deliverable/milestone and how much funding should be released in an intermediate payment installment?
    The list of partners involved in the production of a deliverable/milestone and their respective share - who is involved in a delayed deliverable?
    The dependency of the deliverable/milestone on other deliverables/milestones - who is affected by a delayed deliverable?
    For each deliverable/milestone verifiable progress indicators are defined - how do I monitor progress of a WP?

## Slide 31: Example 1 WP1 has 1.7 M€ funding, 3 deliverables and 4 parties
 | WP1 D1.1: 800 K€ Depends on: - Means of verification: # of software release | D1.2: 600 K€ Depends on: D1.1 Means of verification: # of workshops organized | D1.3: 300 K€ Depends on: WP2 D2.1 Means of verification:
Beneficiary 1 | 25% | 50% | 0%
Beneficiary 2 | 50% | 25% | 50%
Beneficiary 3 | 25% | 25% | 0%
Beneficiary 4 | 0% | 0% | 50%

## Slide 32: Example 2 applied to a real project WP

## Slide 33: Financial monitoring
Not requested by the EC anymore, the consortium can decide to adopt internal financial reporting if useful to the action implementation
+ Simplification of reporting procedures
- Issues
  No easy way to fund project extensions with budget
  No unspent budget to be reallocated to fund deviations in the work plan, for example, a party contributing to a deliverable ‘over budget’ has no way of getting compensation unless another party voluntarily gives up budget
Does the consortium support/not support keeping internal financial reporting?

## Slide 34
Discussion

## Slide 35: Proposed approach for discussion
Governance
  Align with DESCA governance, monitoring and funding distribution approach ⇒ Adoption of periodic internal reports (e.g. every 5 months) and terminating reports. Is the 5 month reporting period acceptable?
  Use of a Dispute Review Expert (DRE). Do you consider the DRE an advantageous dispute resolution approach compared to mediation and arbitration in case of disagreement with a GA resolutions on responsibility in case of no/partial performance?
Monitoring
  Introduce interim report and terminating reports. Is the approach accepted?
  Develop a detailed activity and budget plan expanding Annex 1 and Annex 2:
    Dependencies among deliverables (within and across WPs), WP funding share per deliverable, partner’s share per deliverable, progress verification means per deliverable/milestone. Is the proposed methodology accepted?
Finance
  Funding distribution: 30% of pre-financing followed by further periodic installments. Is proposal acceptable?
  Financial monitoring: do you support/not support internal financial monitoring?