## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 5
18 October 2011
Telcon

## Slide 2: Open Actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110127:2 | Establish a plan for working with the Digital Library | Catherine Gater |  | Feed from iSGTW on DL website. Following up on the upload page. OPEN
20110127:4 | Request profile pages based on the SSO database from CESNET | Catherine Gater |  | Can be done in theory but some privacy issues. Lack a place to display these – building a People Bay in e-ScienceCity OPEN
20110511:1 | Review copyright and trademarking paper | PMB | 18 May | Recommended actions implemented CLOSED
20110511:3 | Look at the trends in traffic to the translated GridCafé sites | Catherine Gater | Next PMB | Stats gathered – presented on the next slide CLOSED
20110511:4 | Make EGI.eu visible on the GridGuide site | Catherine Gater | Next PMB | EGI.eu added to GridGuide at http://www.gridguide.org/gridguide_content.php?id_ge=76 CLOSED
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Discussions with BioMedBridges and ENVRI. No response yet from CRISP. Ready to sign with EUDAT and SHIWA. OPEN
20110511:6 | Request a project review date from the Project Officer | Catherine Gater |  | Date agreed – 8 November 2011 CLOSED
20110511:7 | Raise the GridTalk final payment to partners with the QMUL EC projects office | Steve Lloyd |  | Payment made CLOSED

## Slide 3: GridCafe translation stats
 | Keyword | Page views | Unique Page views | Avg. Time on Page | Bounce Rate
1. | gridcafze | 94 | 13 | 00:00:55 | 28.57%
2. | gridcafe | 12 | 10 | 00:01:04 | 42.86%
3. | cafégrid | 4 | 2 | 00:00:50 | 0.00%
4. | grid café | 4 | 4 | 00:01:56 | 66.67%
5. | learn | 4 | 1 | 00:00:36 | 0.00%
6. | cafe grid | 3 | 2 | 00:00:18 | 0.00%
7. | http://www.gridcafe.org/ | 3 | 2 | 00:00:17 | 50.00%
8. | grid computing | 2 | 2 | 00:00:00 | 100.00%
9. | le mon de tout les site de qu | 2 | 1 | 00:00:08 | 0.00%
10. | www.gridcafe.or | 2 | 1 | 00:00:10 | 0.00%
 | Keyword | Page views | Unique Page views | Avg. Time on Page | Bounce Rate
1. | gridcafe | 20 | 17 | 00:11:48 | 68.75%
2. | grid cafe | 16 | 10 | 00:06:16 | 75.00%
3. | http://grid cafe.org | 11 | 2 | 00:01:29 | 50.00%
4. | grid computing | 9 | 6 | 00:00:17 | 66.67%
5. | http://gridcafe.web.cern.ch/gridcafe/ | 6 | 1 | 00:01:01 | 0.00%
6. | organizaciones virtuales de grid computing | 4 | 2 | 00:02:07 | 0.00%
7. | grid | 3 | 3 | 00:00:00 | 100.00%
8. | que es la computacion | 2 | 1 | 00:00:13 | 0.00%
9. | the placr for | 2 | 1 | 00:01:49 | 0.00%
10. | www.gridcafe.org | 2 | 1 | 00:00:17 | 0.00%
FRENCH SITE
SPANISH SITE

## Slide 4: GridCafe translation stats
 | Source | Page views | Unique Page views | Avg. Time on Page | Bounce Rate
1. | fr.wikipedia.org | 862 | 573 | 00:03:11 | 65.77%
2. | (direct) | 228 | 152 | 00:02:10 | 72.66%
3. | google | 135 | 43 | 00:00:53 | 48.28%
4. | isgtw.org | 90 | 69 | 00:01:03 | 68.97%
5. | e-sciencetalk.org | 51 | 6 | 00:02:11 | 50.00%
 | Source | Page views | Unique Page views | Avg. Time on Page | Bounce Rate
1. | (direct) | 310 | 203 | 00:03:20 | 66.13%
2. | google | 75 | 45 | 00:03:50 | 65.85%
3. | Nodos.typepad.com | 15 | 2 | 00:03:29 | 50.00%
4. | Ctif.madridcapital.educa.madrid.org | 8 | 6 | 00:00:48 | 66.67%
5. | google.com.co | 8 | 5 | 00:00:22 | 25.00%
FRENCH SITE
SPANISH SITE

## Slide 5: GridCafe translation stats
Pages | Pages view | Pages view ( %)
/ | 19 478 | 74,62 %
/index_FR.html | 1 952 | 7,48 %
/index.html | 1 817 | 6,96 %
/index_EN.html | 1 287 | 4,93 %
/index_ES.html | 1 179 | 4,52 %
1 Oct 2010 – 30 September 2011
Gridcafe general page:
17,519 Visits
13,516 Unique visitors
26,104 Pages viewed
1.49 Average pages view
00:01:25 Time passed
71.62 % Rebound
76.23 % New visits
Spanish index page:
1,179 Pages viewed
789 Unique visitors
00:02:34 Time passed
71.21 % Rebound
60.90 % Exit ( %)
French index page:
1,952 Pages viewed
1,222 Unique visitors
00:02:32 Time passed
66.17 % Rebound
56.92 % Exit ( %)

## Slide 6: WP1: Grid policy outreach
Progress
e-ScienceBriefing ‘Asia Pacific Special Issue’ released at the HealthGrid11 meeting and online
e-ScienceBriefing ‘Desktop Grids: connecting everyone to science’ released at the EGITF11 event and online
New e-ScienceBriefing mailing list created – 97 subscribers
GridCasts held at FET11, Climate Change meeting, Trieste and EGITF2011, Lyon
e-Concertation was 22-23 September in Lyon (co-located with EGITF2011) with 109 delegates
Policy events attended: e-IRG in October, Poznan
Recruitment to 0.5FTE post at QMUL, Zara Qadir, started on 14 July 2011

## Slide 7: WP1: Grid policy outreach
Next steps
Recruitment at QMUL for Manisha’s post
Policy event and GridCast at eChallenges, October in Florence
Next Briefing on ??
Future topic ideas
  Data (with EUDAT)
  International dimension of grids
  eGovernment
  Impact indicators
  Digital Agenda for Europe / Horizon 2020
  eInfrastructure governance
  eg GEG report
  Exascale/future computing
  Visualising science & modelling

## Slide 8: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Events page added to include permalinks to the eConcertation meetings
e-ScienceCity / GridCafé
  Russian translation of the GridCafé not as complete as we thought – many pages missing
  Chinese translation of the GridCafé launched on the ASGC site
  e-ScienceCity and CloudLounge sites launched on 22 September at EGIT2011
  Built the new e-ScienceCity landing area on both 2D and 3D sites
GridCast
  GridCasts at EGITF2011, Climate Change Conference, FET11
GridGuide / RTM
  Added PANDA layer to show the ATLAS jobs, more GridGuide sites added to the RTM
  Real Time Monitor has been added to Softpedia's database of software programs for Mac OS
  RTM displayed at EGI User Forum and FET’11
  EGI.eu, CCIN2P3 and MTA SZTAKI sites added to the GridGuide
Digital Library
  iSGTW rss feed added to Digital Library home page
  Working on a document upload page for the e-ScienceTalk site

## Slide 9: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  Which area to develop next? Volunteer computing – big audience, text already prepared in the e-ScienceBriefing and for iSGTW articles.
  Data Garden area with EUDAT
  Common areas ie News, In Debate, People Bay
GridCafé
  BOINC team site being created on the BOINC site
GridCast
  Longer, more editorial posts – some of these have been tried out
  Upcoming GridCasts at eChallenges and ISGC2012
  New name (eScienceCast, eSciCast?) and a new design for the site on Blogger
GridGuide / RTM
  Work on the USP – who is it for? NGIs being encouraged to add sites. NRENs?
  Should we also include projects as well as individual sites?
  CMS data transfer display in the RTM
  Interest from DANTE in an RTM layer showing router traffic

## Slide 10: WP3: iSGTW
Progress
New editorial team working well but OSG contribution has dropped to 0.5FTE over the summer
CERN team now publishing and providing Spotlight and Visual items every week; responsibility for the issue and preview still alternates between the EU and US weekly
Subscriptions hovering around 7800 now the bots are removed
Good impact with social media – Twitter followers and Facebook fans increased, retweets by large accounts eg CERN, NatureNews is driving spikes of traffic to the website
Trying to increase traffic to the Nature Networks forum with new threads and NatureNews follow
iSGTW trademarked at the Swiss Trademark Office
Recruitment of a 0.5FTE Asia-Pacific region editor in progress at ASGC – interview held
Xeno and QMUL discussing the move of the iSGTW site to QMUL for legal rather than cost reasons
Chair role continuing for iSGTW Advisory Board, meetings held on 22 July at Fermilab and 4 October by phone. Next meeting at SC11 in November.

## Slide 11: WP3: iSGTW
Next steps / Issues
Development costs for the site are still met by Fermilab and the site is maintained by Xeno – but funding for this may reduce or disappear
Recruitment to the Asia Pacific editor/assistant role is slow, although ASGC have joined the Board meetings
XSEDE and PRACE are reluctant to engage resources on their side but are willing to collaborate
Large number of new publication names ruled out – currently exploring ideas around a well known name related to computing eg Turing, Babbage, Lovelace

## Slide 12: WP4: Management
Progress
Presentation at British Science Association Science Communication Conference, UK, 25 May
Costs for e-Concertation meeting in Lyon was high, 109 attended, additional booth area for new projects
Weekly meetings continuing with the project team, F2F held at CERN in October
Travel: invitations to ISGC, Taipei, March 2012
Y1 MoUs with e-IRGSP2/3, EUIndiaGrid2, LINKSceem2, WeNMR, CHAIN, DEGISCO, EMI, EGI-InSPIRE all signed
MoU ready to sign with SHIWA and EUDAT
SAGrid and REUNA agreements need to be pursued, as well as ENVRI, CRISP and BioMedBridges

## Slide 13: Project Issues
WP1-WP4
Ensure a good balance of information and contributions from collaborating projects for e-ScienceBriefings
Adding Russian, Chinese etc to the GridCafé
Consultation processes with the iSGTW Advisory Board and unresponsiveness
Lack of sites for GridGuide
New name for iSGTW and development costs
High travel costs for all WPs
Protection of current and future e-ScienceTalk product names
iSGTW subscriber numbers may not reach the milestone

## Slide 14: Y1 Effort
Overall effort achieved in Q1-4 in PMs: per work package
Overall effort achieved in Q1-4 in PMs: per partner
Workpackage | Total plan (PM) | Q1 % achieved | Q2 % achieved | Q3 % achieved | Q4 % achieved | Total Y1 (PM) | YEAR 1 % achieved
WP1 | 46 | 92% | 58% | 66% | 84% | 12.62 | 92%
WP2 | 64 | 75% | 84% | 92% | 68% | 18.47 | 75%
WP3 | 52 | 121% | 111% | 127% | 124% | 22.76 | 121%
WP4-M | 17 | 113% | 85% | 93% | 93% | 5.79 | 113%
WP2-UNF | 8 | 0% | 0% | 0% | 0% | 0 | 0%
WP4-UNF | 5 | 18% | 44% | 16% | 12% | 0.44 | 18%
Total | 192 | 90% | 80% | 89% | 84% | 60.08 | 90%
Partner | Total plan (PM) | Q1 % achieved | Q2 % achieved | Q3 % achieved | Q4 % achieved | Total Y1 (PM) | YEAR 1 % achieved
CERN | 67 | 90% | 83% | 109% | 96% | 23.02 | 90%
APO | 34 | 110% | 99% | 88% | 59% | 11.01 | 110%
QMUL | 47 | 80% | 71% | 76% | 91% | 13.58 | 80%
IMPERIAL | 26 | 80% | 63% | 63% | 71% | 6.47 | 80%
EGI.eu | 18 | 110% | 84% | 89% | 91% | 6.02 | 110%
Total | 192 | 90% | 80% | 89% | 84% | 60.10 | 90%

## Slide 15: Estimated expenditure Y1
Estimated personnel expenditure Q1-4 (in euros): per work package
Workpackage | Q1 Estimated Funding | Q2 Estimated Funding | Q3 Estimated Funding | Q4 Estimated Funding | Cumul Direct | Cumul Indirect | Cumul Eligible | YEAR 1 Estimated Funding
WP1 | 20,829 | 12,999 | 15,201 | 18,757 | 63351.05 | 12670.21 | 76,021 | 67,786
WP2 | 25,341 | 28,148 | 30,851 | 22,965 | 100284.84 | 20056.968 | 120,342 | 107,305
WP3 | 36,815 | 33,658 | 39,010 | 37,884 | 137726.42 | 27545.284 | 165,272 | 147,367
WP4-M | 13,100 | 10,345 | 11,475 | 11,475 | 43360.72 | 8672.144 | 52,033 | 46,396
WP2-UNF | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a
WP4-UNF | n/a | n/a | n/a | n/a | 3762.59 | 752.518 | 4,515 | n/a
Total | 96,085 | 85,150 | 96,537 | 91,082 | 348,486 | 69,697 | 418,183 | 368,854

## Slide 16
Overall EC contribution is 1.3million Euros
Partner | WP1 | WP2 | WP3 | WP4 | Total | Year 1 Plan | Year 1 (Estimated) | Estimated spend (%)
EGI.eu |  |  |  | 187,694 | 187,94 | 68,252 |  | 
QMUL | 223,513 | 56,858 | 40,627 |  | 320,998 | 116,727 |  | 
APO | 28,088 | 154,882 | 28,088 |  | 211,057 | 76,748 |  | 
Imperial |  | 114,181 |  |  | 114,181 | 41,520 |  | 
CERN | 69,164 | 77,562 | 319,344 |  | 466,070 | 169,480 |  | 
Total | 320,764 | 403,485 | 388,057 | 187,694 | 1,300,000 | 472,727 | 368,854 | 78%
Estimated personnel expenditure Y1 (in euros): per partner
Estimated expenditure Y1

## Slide 17: Deliverables and milestones tracking
Complete
In preparation
Overdue
Months | 1 (Sep) | 2 (Oct) | 3 (Nov) | 4 (Dec) | 5 (Jan) | 6 (Feb) | 7 (Mar) | 8 (Apr) | 9 (May) | 10 (Jun) | 11 (Jul) | 12 (Aug) | 13 (Sep) | 14 (Oct) | 15 (Nov)
WP1 Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy |  | D1.2.1 | D1.1 |  | D1.2.2 |  |  | D1.2.3 |  |  | D1.2.4 |  |  | D1.2.5 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.3 |  |  |  | 
T1.3 Events |  |  | MS1 |  |  |  |  |  |  |  |  |  |  | MS2 | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé |  |  |  |  |  |  |  |  |  |  |  |  | D2.2 |  | 
T2.2 GridGuide |  |  |  |  |  |  |  |  |  |  |  | D2.1 |  |  | 
T2.3 GridCast |  | MS4 |  |  |  | MS4 |  |  |  | MS4 |  |  |  | MS4 | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly | D3.1 cont. |  | D3.2 |  |  |  |  |  |  |  |  | D3.4 |  |  | 
T3.2 New media |  |  |  |  | MS7 |  |  |  | D3.3 |  | MS7 |  |  |  | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 | D4.1 | D4.2 | MS10 |  | MS11 | MS10 |  |  | MS10 |  | D4.3 MS12 | MS10 |  | 

## Slide 18: DoW Changes
Transfer of 7390 CHF to CERN for e-Concertation as meeting hosts
Search and trademark registration fees for iSGTW name of 1000 Euros