## Slide 1
www.e-sciencetalk.eu
WP4: Project and Consortium Management
Catherine Gater
e-ScienceTalk Project Coordinator, EGI.eu

## Slide 2: Content
Consumption of effort and resources
Deliverables and milestones
Project metrics
WP4 achievements
Project issues
Summary

## Slide 3
www.e-sciencetalk.eu
Consumption of effort and resources

## Slide 4: WP overview
WP No. | Work package title | Type of activity | Lead partic no. | Lead partic. short name | Personmonths
1 | Policy, impact and sustainability | SUPP | 2 | QMUL | 46
2 | GridCafé, GridCast and GridGuide | SUPP | 3 | APO | 72
3 | International Science Grid This Week | SUPP | 5 | CERN | 52
4 | Management | MGT | 1 | EGI.eu | 22
 | TOTAL |  |  |  | 192

## Slide 5: Y1 achieved effort
Overall effort achieved in Q1-4 in PMs: per work package
Workpackage | Total plan (PM) | Q1 % achieved | Q2 % achieved | Q3 % achieved | Q4 % achieved | Total Y1 (PM) | YEAR 1 % achieved
WP1 | 46 | 92% | 58% | 66% | 93% | 13.33 | 92%
WP2 | 64 | 75% | 84% | 92% | 74% | 19.06 | 75%
WP3 | 52 | 121% | 111% | 127% | 130% | 23.31 | 121%
WP4-M | 17 | 113% | 85% | 93% | 93% | 5.79 | 113%
WP2-UNF | 8 | 0% | 0% | 0% | 0% | 0 | 0%
WP4-UNF | 5 | 18% | 44% | 16% | 40% | 0.64 | 18%
Total | 192 | 90% | 80% | 89% | 91% | 62.13 | 90%
Overall at 90% of planned effort for WP1-4.
Funded effort at 94.5% of planned effort for WP1-4.
Unfunded effort under-reported in Year 1 but activities are ongoing.
Under reporting in WP2 at 75%.
Over reporting in WP3 121%.
Slight over reporting in the management activity due to project start up.
Rebalance WP2/WP3 in Y2 as the partners and staff overlap.

## Slide 6: Y1 achieved effort
Overall effort achieved in Q1-4 in PMs: per partner
Partner | Total plan (PM) | Q1 % achieved | Q2 % achieved | Q3 % achieved | Q4 % achieved | Total Y1 (PM) | YEAR 1 % achieved
CERN | 67 | 90% | 83% | 109% | 96% | 23.00 | 90%
APO | 34 | 110% | 99% | 88% | 92% | 12.89 | 110%
QMUL | 47 | 80% | 71% | 76% | 95% | 13.75 | 80%
IMPERIAL | 26 | 80% | 63% | 63% | 71% | 6.47 | 80%
EGI.eu | 18 | 110% | 84% | 89% | 91% | 6.02 | 110%
Total | 192 | 90% | 80% | 89% | 91% | 62.13 | 90%
Overall at 90% of planned effort for WP1-4.
Slight over reporting for APO and EGI.eu due to design and management overhead for start up.
Slight under reporting for CERN and QMUL.
Adrian Giordani started in PM2 at CERN, just after the project start.
QMUL was under recruited by a 0.5FTE post at the start of the project – new person joined in PM11.

## Slide 7: Effort consumed
Chart: 
| WP1: Policy | WP2: GridCafé | WP3: iSGTW | WP4: Management
% | 23.9583 | 37.5 | 27.0833 | 11.4583
PLANNED
CONSUMED
Chart: 
| WP1: Policy | WP2: GridCafé | WP3: iSGTW | WP4: Management
 | 20.7566 | 30.3783 | 37.4342 | 10.2467

## Slide 8: Partners Y1 expenditure
Overall at 101% of planned spend for Y1.
CERN significant overspending on personnel costs due to exchange rate with the CHF.
CERN additional costs for e-Concertation meeting.
QMUL all categories underspent, only 56% used.
Imperial underspent on travel at 7% used.
EGI.eu central budget for e-Concertation for PY2/3 used for 9th e-Concertation meeting in Lyon 25K.
Partner | Cumul Direct | Cumul Indirect | Cumul Eligible | YEAR 1 Estimated Funding | YEAR 1 Planned Funding | % use
CERN | 234,503 | 130,801 | 365,304 | 249,763 | 169,480 | 147%
APO | 68,817 | 13,763 | 82,580 | 71,887 | 76,748 | 94%
QMUL | 59,986 | 35,992 | 95,978 | 64,185 | 116,727 | 55%
IMPERIAL | 25,694 | 15,416 | 41,110 | 27,492 | 41,521 | 66%
EGI.eu | 64,150 | 12,830 | 76,980 | 66,167 | 68,252 | 97%
Total | 453,150 | 208,802 | 661,952 | 479,494 | 472,728 | 101%

## Slide 9: Project Y1 expenditure
INDIRECT COSTS wrongly calculated into NEF for CERN, QMUL and Imperial (using the indirect 20% flat rate instead of the special transitional flat rate @ 60%)
Personnel overspent at CERN (143%)
Personnel underspent at QMUL (66%) and Imperial (70%)
Travel overspent at EGI.eu but underspent at QMUL (46%) and Imperial (7%)
Central budget e-Concertation meeting:
  15k included in QMUL budget in category Other Costs: Shift 10k to the central budget (EGI.eu)
  25k included in EGI.eu budget (central budget) used at 100%
ALL PARTNERS | Y1 plan | Y1 used | % used
PMs | 65 | 63.25 | 97%
Personnel Costs | 361,937 | 382,038 | 106%
Travel | 36,562 | 30,584 | 84%
Subcontracting | 5,091 | 16,501 | 324%
Other | 38,545 | 15,284 | 40%
e-concertation meeting |  | 8,743 | CENTRAL BUDGET
Total Direct Costs | 442,134 | 453,150 | 102%
Indirect costs | 87,409 | 208,803 | 239%
Total Eligible Costs | 529,543 | 661,952 | 125%
Max. EC Requested Contribution | 472,728 | 479,495 | 101%

## Slide 10: Concertation expenditure
€40K is allocated in the DoW for the e-Infrastructure concertation events to fund logistical costs such as catering, travel and venue costs.
This is allocated as €25K to EGI.eu under WP4 and €15K to QMUL under WP1.
Costs for 9th Concertation meeting, 22-23 September met by EGI.eu as local organisers of the event
Total cost is 24.8K (average 12.4K per event). Remaining budget for 2012 is 15.2K Euros.
8th CONCERTATION MEETING
9th CONCERTATION MEETING
Description | Cost (Euros)
Security | 1,438.00
Catering | 4,574.00
EC diner on the 4th | 318.00
Cleaning | 260.00
Badges | 145.00
Coffee break during the EC meeting | 74.00
TOTAL | 6,809.00
Description | Cost (Euros) | 
Venue main room | 4,502.50 | based 1.5 days
Venue booths area + equipment (panels) | 4,167.00 | based 1.5 days
WIFI, A/V | 1,377.85 | based 120 attendees
Security, cleaning | 934.03 | based 120 attendees
Catering ~18€ | 2,162.40 | based 120 attendees
Breaks 5€ | 1,800.00 | based 120 attendees
Cocktail | 2,649.00 | based 120 attendees
Booths (agINFRA, EUDAT, DASISH @150) | 450.00 | 3 projects
TOTAL | 18,042.78 | 
TOTAL | 24,851.78

## Slide 11
www.e-sciencetalk.eu
Deliverables and Milestones

## Slide 12: Review process
Internal draft ready by day 1 of the PM the report is due
Document internally reviewed by the e-ScienceTalk team – 2 weeks
Document reviewed by the PMB – 1 week
Document submitted at the end of the PM the report is due

## Slide 13: Deliverables
Del. no. | Deliverable name | WP no. | Lead beneficiary |  | Delivery date (PM) | Actual delivery date | Status | Comments
D3.1 | Weekly issues of iSGTW | 3 | CERN | R | 1-33 | 1-3 | Submitted | On time
D1.2.1 | GridBriefings | 1, 2 | QMUL | R | 2 | 2 | Submitted | On time
D4.1 | Dissemination plan | 4 | EGI.eu | R | 2 | 2 | Submitted | On time
D1.1 | Policy engagement strategy | 1 | QMUL | R | 3 | 3 | Submitted | On time
D3.2 | Relaunch of iSGTW with a new name and new underlying content management system | 3, 2 | CERN | O | 3 | 3 | Submitted | On time
D4.2 | Quality assurance guide | 4 | EGI.eu | R | 3 | 3 | Submitted | On time
D1.2.2 | GridBriefings | 1, 2 | QMUL | R | 5 | 5 | Submitted | On time
D1.2.3 | GridBriefings | 1, 2 | QMUL | R | 8 | 8 | Submitted | On time
D3.3 | Strategic report on iSGTW marketing, social media and commercial exploitation | 3 | CERN | R | 9 | 9 | Submitted | On time
D1.2.4 | GridBriefings | 1, 2 | QMUL | R | 11 | 11 | Submitted | On time
D1.3 | Annual impact and sustainability report on e-ScienceTalk products | 1 | QMUL | R | 11 | 11 | Submitted | On time
D2.1 | GridGuide updated integration with the RTM | 2 | Imperial | O | 12 | 12 | Submitted | On time
D3.4 | Report on survey of iSGTW and annual metrics | 3 | CERN | R | 12 | 12 | Submitted | On time
D4.3 | Annual report on feedback and metrics | 4 | EGI.eu | R | 12 | 13 | Submitted | Submitted 2 weeks into PM13 by agreement with the EC

## Slide 14: Milestones
Milestone no. | Milestone name | Work package no | Lead beneficiary | Delivery date from Annex I dd/mm/yyyy | Achieved Yes/No | Actual / achievement date | Comments
MS10.1 | PMB meetings | 4 | EGI.eu | PM1 | Yes | PM1 | 
MS4.1 | GridCasts | 2 | QMUL | PM2 | Yes | PM2 | 
MS1 | E-concertation event | 1, 2, 3 | QMUL | PM3 | Yes | PM3 | 
MS10.2 | PMB meetings | 4 | EGI.eu | PM4 | Yes | PM3 | Held early
MS7 | iSGTW posters and marketing materials | 3, 2 | CERN | PM5 | Yes | PM5 | 
MS4.2 | GridCasts | 2 | QMUL | PM6 | Yes | PM6 | 
MS11 | Dissemination materials | 4 | APO | PM6 | Yes | PM6 | 
MS10.3 | PMB meetings | 4 | EGI.eu | PM7 | Yes | PM5 | Held early
MS4.3 | GridCast | 2 | QMUL | PM10 | Yes | PM9 | Trieste event
MS10.4 | PMB meetings | 4 | EGI.eu | PM10 | Yes | PM9 | Held early
MS7.2 | iSGTW posters and marketing materials | 3, 2 | CERN | PM11 | Yes | PM11 | 
MS12 | Dissemination materials | 4 | APO | PM12 | Yes | PM12 | 

## Slide 15
www.e-sciencetalk.eu
Project metrics

## Slide 16: Project metrics
Recommendation from GridTalk reviewers was to improve tracking of project metrics and impact assessment
Annual Deliverables on Impact (D1.3) and Metrics (D4.3) added to the DoW
Project and work package level metrics gathered quarterly
Changes to the metrics for PY2 are included in D4.3 – starting in PQ5

## Slide 17: Project Metrics Y1
Work Package | Metric no. | Description | Target | Year 1 Achieved | % of Target in Year 1
WP1 | 1.1 | Projects covered | 20 per year | 38 | 190%
 | 1.2 | Reports and briefings circulated | 400 per year | 300 | 75%
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | 36 | 120%
WP2 | 2.1 | Sites on GridGuide | 75 by year 3 | 38 | 50% of end of project target
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | 5 | 100%
 | 2.3 | GridCasts per year | 2 in Europe per year, 1 outside Europe | 16 | 533%
 | 2.4 | New areas in GridCafé | 3, one new area per year | 1 | 100%
WP3 | 3.1 | iSGTW subscribers | 30% increase | 21% | 70% of end of project target
 | 3.2 | Articles on European projects | 50 per year | 108 | 216%
 | 3.3 | Projects in the iSGTW/GridCafé resources section | 100 in total | 194 | 194%
 | 3.4 | iSGTW printed materials distributed | 1000 in total | 330 | 33%

## Slide 18: Project metrics Y2
Work Package | Metric no. | Description | Target Metric | Comments
WP1 | 1.1 | Projects covered | 30 per year | Increased from 20
 | 1.2 | Reports and briefings published | 4 per year | Adjusted to number of reports published not printed
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | Unchanged
WP2 | 2.1 | Sites on GridGuide | 75 | Unchanged
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | Unchanged
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | Increased from 2 in Europe
 | 2.4 | New areas in GridCafé | 3, one new area per year | Unchanged
WP3 | 3.1 | iSGTW subscribers | 30% increase | Including social media followers
 | 3.2 | Articles on European projects | 50 per year | Unchanged
 | 3.3 | Projects in the iSGTW/GridCafé resources section | 150 in total | Increased from 100
 | 3.4 | iSGTW printed materials distributed | 1000 in total | Unchanged

## Slide 19
www.e-sciencetalk.eu
WP4 achievements and project issues

## Slide 20: WP4: Major achievements
Kick-off of the project
  Completion of paperwork Grant Agreement and Consortium Agreement
  Pre-financing distributed to partners (some delay in countersignature of payment by EC)
  Weekly meetings with the project team established
  PMB meetings held, risk register created and monitored
  Project team established, including recruitment of iSGTW Science Writer and Editor and Dissemination Officer
Presentations about the project at:
  EGI Technical Forum2010, eChallenges2010, 8th & 9th e-Infrastructure Concertation Meetings, ASSYST Meeting 2011, BSA Science Communication Conference 2011
Reporting
  Quarterly Reports prepared for Q1-3 in addition to agreed Deliverables and Milestones
Digital Library
  RSS feed from iSGTW to the Digital Library

## Slide 21: WP4: Major achievements
MoUs signed with 8 collaborating projects
  Policy: e-IRGSP2/3
  Collaborations outside Europe: EUIndiaGrid2, LinkSCEEM2, CHAIN
  User community & infrastructures: WeNMR, EMI, EGI-InSPIRE, DEGISCO
International collaborations
  PM is current Chair of EU/US/Asia iSGTW Advisory Board
  Programme Committee and keynote speaker for the 10th International Symposium on Grids and Clouds 2012, Taipei
Events organisation
  Logistics for 8th and 9th e-Infrastructure Concertation events at CERN and Lyon
  Preparation of event budgets, registration, invoicing
  Live video feed for both events in collaboration with CERN and GRDI20

## Slide 22: Project issues
Ensuring a good balance of information and contributions from collaborating projects eg for e-ScienceBriefings
Adding Russian, Chinese and non Roman languages to the GridCafé
Slow addition of new sites for the GridGuide
Consultation processes with the iSGTW Advisory Board can be time consuming
New name for iSGTW – legal challenge to our use of the Digital Scientist
High travel costs for all work packages due to late booking of travel – event organisers late to confirm booths
iSGTW subscriber numbers are not representative of the wider readership achieved – social media and web stats give a more accurate picture
Euro/CHF exchange rate for WP3 – CERN is making far higher contributions to the costs of the project than foreseen

## Slide 23: Mitigations for Year 2
Continue to explore MoUs and collaborations with other projects to ensure balance.
Explore trends in usage of non-English sites to determine which ones to pursue.
Explore new ideas for GridGuide as an area inside the e-ScienceCity website – project oriented structure could be preferable.
Continue Chair role of iSGTW Advisory Board to speed up consultation processes eg on the new name.
Protection of current and future e-ScienceTalk product names.
Work with event organisers in collaborating projects to mitigate high travel costs, aim to be media sponsors if possible and push for journalist and press delegate rates.
Monitor social media figures for iSGTW through the metrics and pursue more media partnerships to include subscription to iSGTW as part of the registration process.

## Slide 24: Summary
Project start up achieved successfully
Recruitment to iSGTW Editor and Science Writer (CERN) and Dissemination Officer (QMUL)
Effort consumption at 90% of planned levels
Estimated costs at 101% of planned levels
All Deliverables and Milestones submitted on time, or early (one 2 weeks late by agreement)
High number of MoUs signed in Year1
Project level metrics largely met or exceeded
High impact for the project in Year1

## Slide 25
www.e-sciencetalk.eu
Additional slides

## Slide 26: Metrics for WP1
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
1.1 | Projects covered | In the e-ScienceBriefings | 15 | 4 | 13 | 17 | 38
1.2 | Reports and briefings circulated | In print or by email | 1 report | 1 report | 1 report | 1 report | 4
1.3 | Countries where reports or briefings are distributed | In print or by email | 36 | 36 | 36 | 36 | 36
1.4 | Policy articles published | In print or online | 3 | 2 | 22 | 7 | 34
1.5 | Policy reports written | In print or online | 1 | 1 | 1 | 1 | 4
1.6 | Printed policy reports circulated | To policy makers | 100 | 0 | 100 | 100 | 300
1.7 | Policy events organised | Number organised | 1 | 0 | 0 | 0 | 1
1.8 | Attendees at policy events | Number of delegates | 111 | 0 | 0 | 0 | 111
1.9 | Collaborating projects to which articles have been distributed | In print or by email | 13 | 6 | 9 | 8 | 36
1.10 | Countries to which articles or reports have been distributed | In print or by email | 36 | 36 | 36 | 36 | 36

## Slide 27: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.1 | Sites on GridGuide | Number of sites included | 30 | 34 | 34 | 38 | 38
2.2 | Bloggers contributing to GridCasts | Average number of bloggers on GridCast | 2 | 3 | 6 | 2 | 3
2.3 | GridCasts per year | Including major and mini GridCasts | 7 | 2 | 5 | 2 | 16
2.4 | New areas of GridCafé | Covering topics other than grid computing | 1 in development | 1 in development | 1 in development | 1 | 1
2.5 | Unique visitors to the GridCafé website | From Google Analytics | 4422 | 4020 | 4490 | 2994 | 15926
2.6 | Page views of the GridCafé website | From Google Analytics | 48676 | 41380 | 48567 | 27788 | 166411
2.7 | Number of bloggers for GridCast | Total number of bloggers | 15 | 7 | 28 | 9 | 59
2.8 | Blog entries | Total number | 92 | 15 | 115 | 22 | 244
2.9 | Podcasts | Total number | 20 | 0 | 36 | 0 | 56
2.10 | Unique visitors to the GridCast | From Google Analytics | 2295 | 1621 | 2765 | 1963 | 8644
2.11 | Page views of the GridCast | From Google Analytics | 5343 | 3526 | 7900 | 3743 | 20512
2.12 | EU sites on GridGuide | European based sites | 24 | 24 | 24 | 28 | 28
2.13 | Non-EU sites on GridGuide | Non-European located sites | 10 | 10 | 10 | 11 | 11

## Slide 28: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.14 | Unique visitors to the GridGuide | From Google Analytics | 345 | 331 | 441 | 645 | 1762
2.15 | Page views of the GridGuide | From Google Analytics | 665 | 536 | 821 | 987 | 3009
2.16 | GridGuide sites on RTM | Total number | 27 | 34 | 34 | 34 | 34
2.17 | Countries in the RTM | Total number | 64 | 64 | 64 | 64 | 64
2.18 | Events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 9 | 0 | 6 | 1 | 16

## Slide 29: Metrics for WP3
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
3.1 | iSGTW subscribers | Registered in the database | 6838 | 7942 | 8074 | 8077 | 8077
3.2 | Articles on European projects | Based on EU funded projects | 33 | 24 | 26 | 25 | 108
3.3 | Projects in the iSGTW/GridCafé resources section | Total number | 134 | 134 | 134 | 194 | 194
3.4 | iSGTW printed materials distributed | At events attended by e-ScienceTalk or by collaborating projects | 120 | 0 | 160 | 50 | 330
3.5 | Issues published | Issued by email to subscribers each week and posted on the website | 13 | 11 | 13 | 14 | 51
3.6 | US articles published | Based on US projects | 30 | 24 | 32 | 27 | 113
3.7 | Worldwide articles published | Based on non US or EU projects | 1 | 7 | 7 | 5 | 20
3.8 | Unique visitors to the website | From Google Analytics | 39,130 | 20,036 | 39,569 | 45,866 | 126,151
3.9 | Page views of the website | From Google Analytics | 74,542 | 42,528 | 64,652 | 84,103 | 265,539
3.10 | Countries visiting the iSGTW website | From Google Analytics | 140 | 148 | 163 | 183 | 193
3.11 | Marketing materials distributed | In print or by email or at events | 120 | 0 | 50 | 50 | 220
3.12 | Survey responses | Through Zoomerang survey tool | No survey issued | No survey issued | No survey issued | 134 | 134

## Slide 30: Metrics for WP4
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
4.1 | Deliverables submitted | By email and online | 6 | 1 | 0 | 3 | 10
4.2 | Milestones agreed | By email and online | 3 | 4 | 2 | 1 | 10
4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 0 | 0 | 1 (by agreement with the EC) | 1
4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 8 posters, 200 pens, 100 annual reports, 150 GridBriefings, 500 pens | 0 | Poster on e-ScienceCity | 0 | Various
4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 206 | 310 | 500 | 418 | 1434
4.6 | Page views of the e-ScienceTalk website | From Google Analytics | 1072 | 1149 | 1422 | 737 | 4380
4.7 | Media releases issued | Issued via Alphagalileo and by email | 1 | 0 | 2 | 0 | 3
4.8 | Press cuttings | Measured by Google Alerts | 3 | 0 | 5 | 5 | 7
4.9 | Events attended | By e-ScienceTalk project team | 9 | 2 | 6 | 1 | 18