## Slide 1
www.e-sciencetalk.eu
Future and Year Two
Catherine Gater
e-ScienceTalk Project Coordinator, EGI.eu

## Slide 2: Content
Impact
Sustainability
Mitigations Year 2
Next projects for Year 2
DoW changes
Summary

## Slide 3: Year One impact
Only one year in, the impact of each e-ScienceTalk product is encouraging and each product is reaching its intended audiences.
iSGTW has increased its sphere of influence (a 21% increase in subscribers) and scope. For Yr 2 we will measure the social media trends, reach and influence.
GridCast blog team is growing in popularity within the community. For Yr 2 examine level of engagement i.e. quality and quantity of commentary.

## Slide 4: Year One impact
e-ScienceBriefings have covered a third more projects than initially targeted and increased their reach to a wider international audience (i.e. 36 countries). In Yr 2, use a more qualitative approach to measure the influence on the intended audience.
GridCafé has widened its scope (clouds, e-science) and is reaching a wider audience (five languages). The site is very popular, raising the general public’s awareness and is referenced widely (134 projects). For Yr 2 measure the impact of the 3D virtual world e-ScienceCity and CloudLounge.
GridGuide has the broadest intended audience (policy makers, general public and researchers). RTM successfully demonstrates what the grid does, and continues to be widely used as a visualisation tool by the community. For Yr 2 integrating the technical and personal aspects of RTM and GridGuide, and exploring integration with e-ScienceCity.

## Slide 5: Sustainability
Evaluate the impact of each product. Quality assurance, measuring impact and continuous evaluation will help to identify further development or re-purposing opportunities. Establish which products are of most value.
Practical steps to sustainability. Identify similar projects and how they became sustainable.
Ongoing maintenance. Identify what will be required to sustain the resource.
Options for financing and partnerships. Finance is the factor that will have most influence, and that will ultimately determine sustainability.
Overview guide to dissemination for EU projects. Based on the extensive experience gained and lessons learnt during both phases of the project.

## Slide 6: Sustainability
e-ScienceBriefings
Will not be produced after the e-ScienceTalk project has ended unless we can find a suitable project or partner to continue their publication. Could potentially be uploaded and monitored in an archived repository.
GridCafé and e-Science City
GridCafé is a long-lasting and sustainable product, having been launched in 2004.
Maintenance of the website in terms of updating content is expected to be relatively low after the e-ScienceCity is developed.
Could seek to build reciprocal and lasting relationships with supporting organisations, which could eventually lead to sponsorship or co-sponsorship.
Create plain static versions of the websites that do not use databases/scripts. Can be stored indefinitely by a project partner so that the resource remains online in an archive.

## Slide 7: Sustainability
GridCast
GridCast was originally produced by CERN and therefore has already been shown to be sustainable.
Voluntary blogging by people outside the e-ScienceTalk project is building an online community of regular contributors.
Moderator needed to ensure content is up-to-date, relevant and appropriate to the users and to recruit bloggers.
GridGuide and Real Time Monitor
GridGuide audience not as well defined as the other e-ScienceTalk products.
e-ScienceTalk plans to investigate who the current audience is, and whether there could be links or in-kind support from collaborating project(s)
The RTM has previously received development funding from GridPP, the UK’s grid for physics.

## Slide 8: Sustainability
iSGTW
iSGTW has built up many loyal subscribers over the years.
e-ScienceTalk will continue to explore commercial sponsorship and in-kind support from collaborating projects.
Due to its partnership with the Fermi National Laboratory in the US, iSGTW cannot currently accept advertising revenues.
Covering more commercial topics could risk alienating the audience we have built so far.
Explore positioning iSGTW as the preferred channel for the research community and major e-infrastructures in Europe.
Contributions of editorial effort from other institutions around the world, including in the Asia-Pacific region.
iSGTW continues to nurture a network of unfunded contributors from a wide range of projects.

## Slide 9: Mitigations for Year 2
Continue to explore MoUs and collaborations with other projects to ensure balance.
Explore trends in usage of non-English sites to determine which ones to pursue.
Explore new ideas for GridGuide as an area inside the e-ScienceCity website – project oriented structure could be preferable.
Continue Chair role of iSGTW Advisory Board to speed up consultation processes eg on the new name.
Explore protection of current and future e-ScienceTalk product names.
Work with event organisers in collaborating projects to mitigate high travel costs, aim to be media sponsors if possible and push for journalist and press delegate rates.
Monitor social media figures for iSGTW through the metrics and pursue more media partnerships to include subscription to iSGTW as part of the registration process

## Slide 10: Next projects for Year 2
WP1: Policy, Impact and Sustainability
Four more e-ScienceBriefings – next one on visualising science and modelling
Expand distribution to new countries and projects
Attend policy events eg e-IRG meetings, eChallenges, Innovation Union meeting, Cloudscape, PRACE, ICT2012
10th e-Infrastructure Concertation meeting

## Slide 11: Next projects for Year 2
WP2: GridCafe, GridGuide and GridCast
New areas of e-ScienceCity, next is the Volunteer Garage.
GridCast new design and casts from events such as SC11, ISGC2012, EGI Community Forum 2012.
Integrate GridGuide into the e-ScienceCity.
RTM new sites and data transfers for PANDA data.
Launch the 3D pilot site in NewWorldGrid.

## Slide 12: Next projects for Year 2
WP3: iSGTW
New editor for Asia Pacific region.
Collaboration with PRACE and XSEDE.
Increase user interactivity with the site.
Expand outreach through social media.
Increase subscribers through media partnerships for events with new user communities.

## Slide 13: Next projects for Year 2
WP4: Management
MoUs with ESFRI support projects and others eg EUDAT, ENVRI, BioMedBridges, SAGrid, REUNA.
International collaborations eg ISGC2012.
Balance WP2/WP3 effort reporting.
Control travel and other costs.

## Slide 14: DoW budget changes
A redistribution of budget to the central budget(1) is envisaged to cover general dissemination travel costs and provide a reserve for the travels of unfunded participants.
  QMUL OTHER COSTS Budget: 22k  shift 15k
    (of which 5k to cover the Citizen Cyberscience Summit media sponsorship paid by EGI.eu)
  Imperial TRAVEL Budget 10k:  shift 5k
  including e-concertation meeting
Costs expected for future legal searches and possible maintenance for the iSGTW website.

## Slide 15: Summary
Good impact in Year One for the e-ScienceTalk products.
Ideas for expansion of impact in Year Two.
Sustainability activities exploring options for beyond e-ScienceTalk.
Plans for Year Two on track.
Small modifications to the DoW in the area of sub-contracting to cover e-Concertation costs, legal searches and possible website maintenance.

## Slide 16
www.e-sciencetalk.eu
Additional slides

## Slide 17: Metrics for WP1
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
1.1 | Projects covered | In the e-ScienceBriefings | 15 | 4 | 13 | 17 | 38
1.2 | Reports and briefings circulated | In print or by email | 1 report | 1 report | 1 report | 1 report | 4
1.3 | Countries where reports or briefings are distributed | In print or by email | 36 | 36 | 36 | 36 | 36
1.4 | Policy articles published | In print or online | 3 | 2 | 22 | 7 | 34
1.5 | Policy reports written | In print or online | 1 | 1 | 1 | 1 | 4
1.6 | Printed policy reports circulated | To policy makers | 100 | 0 | 100 | 100 | 300
1.7 | Policy events organised | Number organised | 1 | 0 | 0 | 0 | 1
1.8 | Attendees at policy events | Number of delegates | 111 | 0 | 0 | 0 | 111
1.9 | Collaborating projects to which articles have been distributed | In print or by email | 13 | 6 | 9 | 8 | 36
1.10 | Countries to which articles or reports have been distributed | In print or by email | 36 | 36 | 36 | 36 | 36

## Slide 18: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.1 | Sites on GridGuide | Number of sites included | 30 | 34 | 34 | 38 | 38
2.2 | Bloggers contributing to GridCasts | Average number of bloggers on GridCast | 2 | 3 | 6 | 2 | 3
2.3 | GridCasts per year | Including major and mini GridCasts | 7 | 2 | 5 | 2 | 16
2.4 | New areas of GridCafé | Covering topics other than grid computing | 1 in development | 1 in development | 1 in development | 1 | 1
2.5 | Unique visitors to the GridCafé website | From Google Analytics | 4422 | 4020 | 4490 | 2994 | 15926
2.6 | Page views of the GridCafé website | From Google Analytics | 48676 | 41380 | 48567 | 27788 | 166411
2.7 | Number of bloggers for GridCast | Total number of bloggers | 15 | 7 | 28 | 9 | 59
2.8 | Blog entries | Total number | 92 | 15 | 115 | 22 | 244
2.9 | Podcasts | Total number | 20 | 0 | 36 | 0 | 56
2.10 | Unique visitors to the GridCast | From Google Analytics | 2295 | 1621 | 2765 | 1963 | 8644
2.11 | Page views of the GridCast | From Google Analytics | 5343 | 3526 | 7900 | 3743 | 20512
2.12 | EU sites on GridGuide | European based sites | 24 | 24 | 24 | 28 | 28
2.13 | Non-EU sites on GridGuide | Non-European located sites | 10 | 10 | 10 | 11 | 11

## Slide 19: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.14 | Unique visitors to the GridGuide | From Google Analytics | 345 | 331 | 441 | 645 | 1762
2.15 | Page views of the GridGuide | From Google Analytics | 665 | 536 | 821 | 987 | 3009
2.16 | GridGuide sites on RTM | Total number | 27 | 34 | 34 | 34 | 34
2.17 | Countries in the RTM | Total number | 64 | 64 | 64 | 64 | 64
2.18 | Events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 9 | 0 | 6 | 1 | 16

## Slide 20: Metrics for WP3
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
3.1 | iSGTW subscribers | Registered in the database | 6838 | 7942 | 8074 | 8077 | 8077
3.2 | Articles on European projects | Based on EU funded projects | 33 | 24 | 26 | 25 | 108
3.3 | Projects in the iSGTW/GridCafé resources section | Total number | 134 | 134 | 134 | 194 | 194
3.4 | iSGTW printed materials distributed | At events attended by e-ScienceTalk or by collaborating projects | 120 | 0 | 160 | 50 | 330
3.5 | Issues published | Issued by email to subscribers each week and posted on the website | 13 | 11 | 13 | 14 | 51
3.6 | US articles published | Based on US projects | 30 | 24 | 32 | 27 | 113
3.7 | Worldwide articles published | Based on non US or EU projects | 1 | 7 | 7 | 5 | 20
3.8 | Unique visitors to the website | From Google Analytics | 39,130 | 20,036 | 39,569 | 45,866 | 126,151
3.9 | Page views of the website | From Google Analytics | 74,542 | 42,528 | 64,652 | 84,103 | 265,539
3.10 | Countries visiting the iSGTW website | From Google Analytics | 140 | 148 | 163 | 183 | 193
3.11 | Marketing materials distributed | In print or by email or at events | 120 | 0 | 50 | 50 | 220
3.12 | Survey responses | Through Zoomerang survey tool | No survey issued | No survey issued | No survey issued | 134 | 134

## Slide 21: Metrics for WP4
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
4.1 | Deliverables submitted | By email and online | 6 | 1 | 0 | 3 | 10
4.2 | Milestones agreed | By email and online | 3 | 4 | 2 | 1 | 10
4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 0 | 0 | 1 (by agreement with the EC) | 1
4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 8 posters, 200 pens, 100 annual reports, 150 GridBriefings, 500 pens | 0 | Poster on e-ScienceCity | 0 | Various
4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 206 | 310 | 500 | 418 | 1434
4.6 | Page views of the e-ScienceTalk website | From Google Analytics | 1072 | 1149 | 1422 | 737 | 4380
4.7 | Media releases issued | Issued via Alphagalileo and by email | 1 | 0 | 2 | 0 | 3
4.8 | Press cuttings | Measured by Google Alerts | 3 | 0 | 5 | 5 | 7
4.9 | Events attended | By e-ScienceTalk project team | 9 | 2 | 6 | 1 | 18