MPI VT report
VT MPI within EGI
Community Forum 2012
Álvaro Simón (CESGA)
Zdnek Sustr (CESNET)

---
Outline
Outline
- Introduction
  - Objectives
  - Motivation
  - Expected Output
- Status Report
  - Open tasks and progress
  - Open issues
- Future work

---
Introduction
Introduction
- MPI VT created in November 2011
  - Supposed to end on May 2012
  - Wiki page: https://wiki.egi.eu/wiki/VT_MPI_within_EGI
  - Mailing list: vt-mpi@mailman.egi.eu
- Objectives
  - Collaborate with MPI user communities
  - Promote MPI deployment
  - Enhance MPI experience and support for EGI users.
- Output
  - Improve the communications between MPI users and developers within EGI SA3.
  - Improve / create new MPI documentation for EGI users and administrators.
  - Find and detect current issues and bottlenecks related with MPI jobs.
  - Set up a VO on EGI with site committed to support MPI jobs.

---
Documentation
Task 1: Documentation
- Motivation:
  - MPI documentation was fragmented in different places.
  - Too much site admin / infrastructure oriented.
- Progress:
  - Documentation reviewed and extended by MPI VT members.
  - MPI Administrator guide: https://wiki.egi.eu/wiki/MAN03
    - new sections to clarify MPI doubts
  - Working on an MPI user guide
  - Propose to concentrate documentation under a single endpoint

---
Information System
Task 2: IS
- Motivation:
  - Few sites are publishing correctly MPI tags and flavours
    - Some MPI info is omitted, missing or incorrect.
    - Incoherent information published by queues supporting MPI
- Progress:
  - Survey the information published by sites
  - Inspect which GLUE 1.3/2.0 variables could be used in the MPI context and ask for its correct implementation
    - GLUE 1.3 “MaxSlotsPerJobs” could be already used but only one site publishes a different value wrt the default “999999999”
    - Detected problems in the CPU / WallClockTime relationship published by sites. May lead to the early killing of parallel jobs

---
Nagios probes
Task 3: Nagios Probes
- Motivation:
  - Current SAM nagios probes are quite simple.
    - It does not detect if a MPI sites is really working fine or not.
- Progress:
  - A new set of nagios probes specifications were created by MPI members: https://wiki.egi.eu/wiki/VT_MPI_within_EGI:Nagios
    - Probe to check information system
    - Set of probes to check the MPI functionality (EGEE MPI WG recommendations)
  - Request the creation of a new GOCDB Service Type
    - GOCDB acting like an ITIL CMDB: all configuration items should be registered
    - Release the dependency from the information system
    - Allows accurate infrastructure information about infrastructure status

---
Accounting
Task 4: Accounting
- Motivation:
  - The only way to recognize a parallel jobs in the accounting system and looking for jobs with efficiency >1
  - APEL is not ready to registry MPI usage records.
    - This work is on progress and tracked by JRA1.4 task and EMI.
    - New APEL with MPI capabilities will be ready at the end of summer.
- Progress:
  - MPI VT members are in contact with EMI developers to describe the parallel usage record for the different batch systems.
  - Hopefully this will lead to some requirements to an accounting system able to correctly record parallel usage

---
Batch System
Task 5: LRMS status
- Motivation:
  - Detect LRMS MPI issues. Check MPI LRMS status support.
- Progress:
  - CREAM GE EMI release fully supports MPI. Tested by MPI VT members.
  - Issue with Torque / Maui MPI support (GGUS tickets #57828 #67870)
    - Not supported by EMI but by a third party.
    - EPEL includes torque server / client packages and an external EMI repo includes MAUI updates.
  - Issue raised to EGI SA1/2 and to EMI

---
VO
Task 6: MPI-Kickstart VO
- Motivation:
  - MPI VO bring together sites and users interested in MPI.
  - This VO is NOT intended for everyday use by all users wishing to use MPI.
  - The main reason for its establishment is to collect experience that will be later adopted by regular VOs.
- Progress:
  - MPI-Kicktart VO established and populated
    - MPI VO configuration is available in the MPI VT wiki page.
  - Resources currently provided by CESGA and CESNET
    - More welcome
  - Resolving issues as they arrive

---
Sites Feedback
  - NGI Italy has presented a survey about MPI usage. This is allow the detection of problems from user perspective. Slides available in indico: https://www.egi.eu/indico/materialDisplay.py?contribId=1&materialId=slides&confId=828
  - NGI_SK has presented a report to check MPI JDL attributes required by different experiments: https://www.egi.eu/indico/getFile.py/access?contribId=4&resId=0&materialId=0&confId=828

---
Issues
Open Issues
- Batch system support: It was discussed with EMI.
  - Torque batch system is not supported by EMI. Is a third-party piece of software.
  - Torque server/client are maintained by Steve Traylen (not in EMI). These packages are included into EPEL repo.
  - MAUI scheduler is also maintained by Steve Traylen (not in EMI) and updates an external CERN repo.

---
Future Work
Future Work
- Continue to unify and simplify MPI documentation
- Inspect how the IS schema can adjust to specific LRMS policies, and enforce the correct values
  - May involve interaction with LRMS IP developers
- Tested “new” probes functionality
  - Should be developed by SA3
- Include new sites to support VO MPI
  - For testing purposes.
- Provide requirements to a new accounting system able to support MPI jobs

---
Questions
- Questions?