## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 6
17 January 2012
Telcon

## Slide 2: Open Actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110127:2 | Establish a plan for working with the Digital Library | Catherine Gater |  | Support for DL will end in May 2012. OPEN
20110127:4 | Request profile pages based on the SSO database from CESNET | Catherine Gater |  | People Bay to be discussed at project F2F meeting, 17 Jan, exact requirements to be sent to CESNET OPEN
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Discussions with BioMedBridges and ENVRI. No response yet from CRISP. Signed with EUDAT and SHIWA. OPEN
20111018:1 | Allocate checking the trademarking and copyright actions to a member of staff. | Bob Jones | Next PMB | OPEN
20111018:2 | Advertise the translated GridCafé sites to CHAIN, GISELA and SAGrid. | Catherine Gater | Next PMB | Advertising campaign planned for e-ScienceCity and translated sites. OPEN
20111018:3 | Send an MoU template or letter of intent to NewWorldGrid via APO. | Catherine Gater | Next PMB | Template sent but no response so far. OPEN

## Slide 3: WP1: Grid policy outreach
Progress
Recruitment at QMUL for Manisha’s post – interviews Friday 20, 4 candidates
Policy event and GridCast at eChallenges, October in Florence
Gridcast at SC11 in November
Future GridCasts at CCC Summit, London, CloudScape IV, Brussels and ISGC12, Taipei (February) and EGI Community Forum, Munich (March)
EUDAT Users Meeting, Barcelona, March – should we attend?
Next Briefing on Networking with DANTE etc
Zara Qadir working 0.8FTE until the end of February
Other consultants at QMUL for GridCasts?

## Slide 4: WP1: Grid policy outreach
Next steps
Plan for gathering feedback, including 6 monthly reports
Further work on sustainability and measuring the sources of traffic to the sites
Future topic ideas for briefings
  Data (with EUDAT)
  International dimension of grids
  eGovernment
  Impact indicators - eNVENTORY
  Digital Agenda for Europe / Horizon 2020
  eInfrastructure governance
  eg GEG report
  Exascale/future computing
  Visualising science & modelling – next?

## Slide 5: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Adding translations of e-ScienceBriefings in Spanish
e-ScienceCity / GridCafé
  Volunteer garage area – text in final stages, illustrations in preparation
  Need to advertise the new website – plan an html ‘poster’ and email footer
  Problem with having duplicate GridCafe sites – Google sees the content as ‘stolen’ and does not index it
GridCast
  GridCasts at SC11, Seattle and eChallenges, Florence
  Staying with the existing name for now, but the site needs to be updated.
GridGuide / RTM
  Data layer added in collaboration with DANTE showing router traffic
  Two webstart versions available, with and without DANTE data – PANDA layer added as default
  Working on a new design for the RTM website
  Could instead tag ALL database content eg projects, people, articles, blogs as being from a site or country to increase the number of guides.
Digital Library
  Support for this ending May 2012
  Should we offer to support it after this? Or provide our own version or use different one eg OpenAIRE

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  New areas in order: volunteer garage, supercomputing, networking and data garden
  Common areas ie News, In Debate, People Bay being developed
  Need to trademark e-ScienceCity and e-ScienceIsland
GridCafé
  Need a handover date for the old and new versions of GridCafe as both sites cannot run with the same content
GridCast
  Need to have a presence at events outside the usual community to increase the audience and advertise products such as iSGTW.
GridGuide / RTM
  CMS data transfer display in the RTM currently in development but a step change for year 2 is needed
  Indexed/tagged content could be displayed through a map interface – similar to the EGI trainers and events map interface at http://www.egi.eu/user-support/ngi_support/
  Need to make sure there is information that is displayed when you click on a site in the RTM that is linked to the GridGuide.
  A 2D version that could be mapped onto a sphere is proposed, and a version driven by a Kinect interface possible in the current version of WorldWideWind.

## Slide 7: WP3: iSGTW
Progress
OSG contribution has dropped to 0.5FTE over the summer – trying to interest other US agencies in funding this contribution
CERN team now publishing and providing Spotlight and Visual items every week; responsibility for the issue and preview still alternates between the EU and US weekly – this is working but previews on US side often late
Subscriptions hovering around 7800 - 8000 now the bots are removed – tracking social media as well
Good impact with social media – Twitter followers and Facebook fans continuing to increase, retweets by large accounts eg CERN, NatureNews is driving spikes of traffic to the website
Attempt to increase traffic to the Nature Networks forum with new threads and NatureNews follow was not really successful
Vivian Chang recruited as the 0.5FTE Asia-Pacific region editor at ASGC – announcement this week
Move of the iSGTW site to QMUL should take place soon
iSGTW Advisory Board, meeting held at SC11 in November, next one TBA

## Slide 8: WP3: iSGTW
Next steps / Issues
Development costs for the site are still met by Fermilab and the site is maintained by Xeno – but funding for this may reduce or disappear
New name issue is still outstanding – the reviewers recommended e or d-science based title and OSG has not vetoed this
Currently exploring existing titles in these areas to propose to the Board.
XSEDE and PRACE are reluctant to engage resources on their side but are willing to collaborate – but this has not been very concrete yet
Need to increase subscriber numbers as well as social media numbers
Continuing glitches with publishing, always for different reasons!

## Slide 9: WP4: Management
Progress
Review report received – recommendations in the areas of metrics and sustainability
One more e-Concertation meeting expected in November 2012, Brussels
Weekly meetings continuing with the project team
Travel: invitations to ISGC, Taipei, March 2012
MoUs signed with SHIWA (December) and EUDAT (January)
SAGrid and REUNA agreements need to be pursued, as well as ENVRI, CRISP and BioMedBridges
F2F at CERN on 17 to plan the second half of the project

## Slide 10: Project Issues
WP1-WP4
Ensure a good balance of information and contributions from collaborating projects for e-ScienceBriefings
Adding Russian, Chinese etc to the GridCafé
Consultation processes with the iSGTW Advisory Board and unresponsiveness
Lack of sites for GridGuide
New name for iSGTW and development costs
High travel costs for all WPs
Protection of current and future e-ScienceTalk product names
iSGTW subscriber numbers may not reach the milestone

## Slide 11: Y1 Effort
Overall effort achieved in Q5 in PMs: per work package
Overall effort achieved in Q5 in PMs: per partner
Workpackage | 6.25 | Sep | Oct | Nov | Total | Linear Plan | Q5 % achieved
WP1 | 46 | 1.61 | 1.44 | 1.31 | 4.36 | 4.2 | 104%
WP2 | 64 | 1.98 | 1.78 | 1.45 | 5.21 | 5.8 | 90%
WP3 | 52 | 1.58 | 2.28 | 1.89 | 5.75 | 4.7 | 122%
WP4-M | 17 | 0.42 | 0.69 | 0.56 | 1.67 | 1.5 | 111%
WP2-UNF | 8 | 0 | 0 | 0 | 0 | 0.7 | 0%
WP4-UNF | 5 | 0.08 | 0.06 | 0.06 | 0.2 | 0.5 | 40%
Total | 192 | 5.67 | 6.25 | 5.27 | 17.19 | 17.5 | 98%
Partner | Total plan (PM) | Sep | Oct | Nov | Total | Linear Plan | Q5 % achieved
CERN | 67 | 1.75 | 2.31 | 2.33 | 6.39 | 6.1 | 105%
APO | 34 | 1.13 | 0.89 | 0.69 | 2.71 | 3.1 | 87%
QMUL | 47 | 1.81 | 1.72 | 1.08 | 4.61 | 4.3 | 107%
IMPERIAL | 26 | 0.53 | 0.61 | 0.53 | 1.67 | 2.4 | 70%
EGI.eu | 18 | 0.45 | 0.72 | 0.62 | 1.79 | 1.6 | 112%
Total | 192 | 5.67 | 6.25 | 5.25 | 17.17 | 17.5 | 98%

## Slide 12: Estimated expenditure Q5
Estimated personnel expenditure Q5 (in euros): per work package
Workpackage | Sep | Oct | Nov | Cumul Direct | Cumul Indirect | Cumul Eligible | Q5 Estimated Funding
WP1 | 7,942 | 7,219 | 6,912 | 22,073 | 4,415 | 26,487 | 23,618
WP2 | 10,428 | 9,392 | 7,753 | 27,574 | 5,515 | 33,088 | 29,504
WP3 | 9,436 | 13,783 | 11,737 | 34,956 | 6,991 | 41,947 | 37,403
WP4-M | 3,484 | 5,580 | 4,490 | 13,554 | 2,711 | 16,265 | 14,503
WP2-UNF | n/a | n/a | n/a | 0 | 0 | 0 | n/a
WP4-UNF | 585 | 469 | 705 | 1m761 | 352 | 2,113 | n/a
Total | 31,875 | 36,444 | 31,598 | 99,917 | 19,983 | 119,900 | 105,027

## Slide 13: Deliverables and milestones tracking
Complete
In preparation
Overdue
Months | 13 (Sep) | 14 (Oct) | 15 (Nov) | 16 (Dec) | 17 (Jan) | 18 (Feb) | 19 (Mar) | 20 (Apr) | 21 (May) | 22 (Jun) | 23 (Jul) | 24 (Aug)
WP1 Policy |  |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy |  | D1.2.5 |  |  | D1.2.6 |  |  | D1.2.7 |  |  | D1.2.8 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.4 | 
T1.3 Events |  | MS2 |  |  |  |  |  |  |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé | D2.2 |  |  |  |  |  |  |  |  |  |  | 
T2.2 GridGuide |  |  |  |  |  | MS5 |  |  |  |  | D2.3 | 
T2.3 GridCast |  | MS4 |  |  |  | MS4 |  |  |  | MS4 |  | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  | MS8 |  |  |  |  |  |  | D3.5
T3.2 New media |  |  |  |  | MS7 |  |  |  |  |  | MS7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS13 | MS10 |  |  | MS10 |  | D4.4 MS14

## Slide 14: DoW Amendment
Budget changes proposal |  |  |  |  |  | 
A redistribution of budget to the central |  |  |  |  |  | 
budget(1) is envisaged to cover general |  |  |  |  |  | 
dissemination travel costs and provide a reserve |  |  |  |  |  | 
Creation of a Central Budget in EGI.eu hands for the travels of unfunded participants. |  |  |  |  |  | 
– QMUL OTHER COSTS Budget: 22k shift 15k |  |  |  | 15000 |  | 
Of which 5k to cover the Kings College sponsorship paid by EGI.eu |  |  |  |  |  | 
– Imperial TRAVEL Budget 10k: shift 5k |  |  |  | 5000 |  | 
INITIAL BUDGET TABLE |  |  |  |  |  | 
Participant number | Participant short name | Estimated eligible costs (whole duration of the project) |  |  |  | 
 |  | Coordination/ Support (A) | Management (B) | Other C | Total A+B+C | Requested EU contribution
1 | EGI.eu | 0.00 | 210,498.00 | 0.00 | 210,498.00 | 187,694.00
2 | QMUL | 359,998.00 | 0.00 | 0.00 | 359,998.00 | 320,998.00
3 | APO | 236,700.00 | 0.00 | 0.00 | 236,700.00 | 211,057.00
4 | Imperial | 128,054.00 | 0.00 | 0.00 | 128,054.00 | 114,181.00
5 | CERN | 520,995.00 | 0.00 | 0.00 | 520,995.00 | 466,070.00
 |  | 1,245,747.00 | 210,498.00 | 0.00 | 1,456,245.00 | 1,300,000.00
AMENDMENT N1 |  |  |  |  |  | 
Participant number | Participant short name | Estimated eligible costs (whole duration of the project) |  |  |  | 
 |  | Coordination/ Support (A) | Management (B) | Other C | Total A+B+C | Requested EU contribution
1 | EGI.eu | 20,000.00 | 210,498.00 | 0.00 | 230,498.00 | 187,694.00
2 | QMUL | 344,998.00 | 0.00 | 0.00 | 344,998.00 | 320,998.00
3 | APO | 236,700.00 | 0.00 | 0.00 | 236,700.00 | 211,057.00
4 | Imperial | 123,054.00 | 0.00 | 0.00 | 123,054.00 | 114,181.00
5 | CERN | 520,995.00 | 0.00 | 0.00 | 520,995.00 | 466,070.00
 |  | 1,245,747.00 | 210,498.00 | 0.00 | 1,456,245.00 | 1,300,000.00