## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 7
13 March 2012
Telcon

## Slide 2: Open Actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110127:2 | Establish a plan for working with the Digital Library | Catherine Gater |  | Support for DL will end in May 2012, EC to be informed. OPEN
20110127:4 | Request profile pages based on the SSO database from CESNET | Catherine Gater |  | Requirements to be sent to CESNET. OPEN
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Further discussions with BioMedBridges, ENVRI and CRISP. Signed with N4U. OPEN
20111018:1 | Allocate checking the trademarking and copyright actions to a member of staff. | Bob Jones | Next PMB | OPEN
20111018:2 | Advertise the translated GridCafé sites to CHAIN, GISELA and SAGrid. | Catherine Gater | Next PMB | Leaflet produced, distributed to CRISP and at ISGC2012. OPEN
20111018:3 | Send an MoU template or letter of intent to NewWorldGrid via APO. | Catherine Gater | Next PMB | Template sent but no response so far. OPEN
20120117:1 | Contact EUDAT about User Meeting, 7 March | Catherine Gater | By March | Attendance not recommended. CLOSED
20120117:2 | Confirm the approval of the ToR and date of next meeting | Catherine Gater | Next PMB | ToR confirmed, date of next meeting TBA. OPEN

## Slide 3: WP1: Grid policy outreach
Progress
Recruitment at QMUL for Manisha’s post – Stefan Janusz started on 27 Feb 2012.
Abstract prepared for eChallenges, October in Lisbon
Gridcasts at CCC Summit, London, CloudScape IV, Brussels and ISGC12, Taipei (February)
Next GridCast at EGI Community Forum, Munich (March)
EUDAT Users Meeting, Barcelona, March – not recommended to attend, go to the meeting in the autumn instead
Briefing on Networking issued at the end of Feb at ISGC2012
Next Briefing on Visualisation for the end of April
Zara Qadir working 0.8FTE until the end of March
Upcoming policy events: ERF Impact Workshop, eIRG meeting, CRIS2012

## Slide 4: WP1: Grid policy outreach
Next steps
Feedback collection on e-ScienceBriefings and Volunteer Garage
Further work on sustainability and measuring the sources of traffic to the sites
Future topic ideas for briefings
  Data (with EUDAT)
  International dimension of grids
  eGovernment
  Impact indicators - eNVENTORY
  Digital Agenda for Europe / Horizon 2020
  eInfrastructure governance
  Exascale/future computing
  Visualising science & modelling – next?
  Open Science
  Costs of cloud, e-infrastructure
  Tech transfer eg openLab, CRISP

## Slide 5: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Adding partners and MoU collaborations to the website
e-ScienceCity / GridCafé
  Volunteer garage area – launched at the Citizen Cyberscience Summit, London
  Need to advertise the new website – leaflet prepared, add email footer
  Moved to individual URLs for each area, now indexed by Google
GridCast
  GridCasts at CCC, London, Cloudscape IV, Brussels, ISGC2012
  outGRID event, Geneva, 7 videos prepared, getting permission to release.
GridGuide / RTM
  Data layer now available as a separate webstart version- looking at how to show data transfers graphically
  Upgraded to new version of WorldWideWind, will improve 2D version eg for projection on a globe
  Working on a new design for the RTM website
  Could instead tag ALL database content eg projects, people, articles, blogs as being from a site or country to increase the number of guides.
Digital Library
  Support for this ending May 2012
  Waiting to resolve iSGTW issues before involving the EC

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  New areas in order: supercomputing, networking and data garden
  Common areas ie News, In Debate, People Bay being developed
  Need to trademark e-ScienceCity and e-ScienceIsland – URLs all purchased
GridCafé
  Need a handover date for the old and new versions of GridCafe as both sites cannot run with the same content
GridCast
  Need to have a presence at events outside the usual community to increase the audience and advertise products such as iSGTW.
GridGuide / RTM
  CMS data transfer display in the RTM currently in development but a step change for year 2 is needed
  Indexed/tagged content could be displayed through a map interface – similar to the EGI trainers and events map interface at http://www.egi.eu/user-support/ngi_support/
  Need to make sure there is information that is displayed when you click on a site in the RTM that is linked to the GridGuide – added 25 sites to meet the milestone, but additional content needed
  Kinect interface possible, just need to map the controls across – use for SC12?

## Slide 7: WP3: iSGTW
Progress
OSG contribution frozen from the end of March – MB to stay on an additional month or two
Paul Avery contacting the NSF PIs for staffing support, perhaps at Indiana? Ruth Pordes drafting a bid document and a draft support letter to the NSF is with the EC for comment.
Need to identify underspent budget areas to carve out funds for the website support – ending Sep2012
JH leaving CERN at the end of March – recruitment underway, closing date 18 March
Made contact with Reagan Moore of IRODS/RENCI at ISGC2012 – leads and intro content provided
Subscriptions hovering around 8000
Continued good impact of social media policy – Twitter followers and Facebook fans continuing to increase, retweets by large accounts eg CERN, NatureNews is driving spikes of traffic to the website
Some additional traffic to the Nature Networks forum recently
Vivian Chang, slightly slow start as the 0.5FTE Asia-Pacific region editor– actively participated at the ISGC2012 event on filming and blogging, and has now submitted content to iSGTW on the QCN
Move of the iSGTW site to QMUL should take place soon but slow progress while Alex in Japan
iSGTW Advisory Board, next one TBA

## Slide 8: WP3: iSGTW
Next steps / Issues
Identifying funds from the budget for freelance support – writing (JH), maintenance (Xeno).
Xeno has a list of priority tasks for the March maintenance – will identify further tasks for April
New name issue is still outstanding – the reviewers recommended e or d-science based title and URLs have been purchased. But no financial resources currently available for making the change over
XSEDE and PRACE are still reluctant to engage resources on their side – no contact from PRACE despite repeated efforts
Need to increase subscriber numbers as well as social media numbers
Glitches with publishing fewer recently, but US preview now always late
Some last minute changes of content due to keeping up with events

## Slide 9: WP4: Management
Progress
Face to face meeting held at CERN on 17 January to plan approaches to the recommendations in the areas of metrics and sustainability
One more e-Concertation meeting expected in November 2012, Brussels
Weekly meetings continuing with the project team
Travel: invitations to Crete for 2 members of the team for the CRISP meeting, ENVRI (Vienna) and GISELA-CHAIN (Mexico City)
MoU signed with N4U (January), service proposal sent to CRISP for discussion by the Board, will meet them at ICRI2012
SAGrid and REUNA agreements need to be pursued, as well as DiscovertheCosmos, BioMedBridges, new projects in recent call eg Helix Nebula
F2F at EGICF in Munich planned
Year 2 amendment session open finalising budget changes, DoW updated
Year 1 costs approved and payments to partners with the EC for signing – ceiling now reached, no further payments until end of project

## Slide 10: Project Issues
WP1-WP4
Ensure a good balance of information and contributions from collaborating projects for e-ScienceBriefings
Adding Russian, Chinese etc to the GridCafé
Funding for iSGTW – editorial effort and web support
Lack of sites for GridGuide – end of project milestone a concern
New name for iSGTW and development costs – no funds available
High travel costs for all WPs – funding for 2 people for CRISP meeting
Protection of current and future e-ScienceTalk product names
iSGTW subscriber numbers may not reach the milestone

## Slide 11: Deliverables and milestones tracking
Complete
In preparation
Overdue
Months | 13 (Sep) | 14 (Oct) | 15 (Nov) | 16 (Dec) | 17 (Jan) | 18 (Feb) | 19 (Mar) | 20 (Apr) | 21 (May) | 22 (Jun) | 23 (Jul) | 24 (Aug)
WP1 Policy |  |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy |  | D1.2.5 |  |  | D1.2.6 |  |  | D1.2.7 |  |  | D1.2.8 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.4 | 
T1.3 Events |  | MS2 |  |  |  |  |  |  |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé | D2.2 |  |  |  |  |  |  |  |  |  |  | 
T2.2 GridGuide |  |  |  |  |  | MS5 |  |  |  |  | D2.3 | 
T2.3 GridCast |  | MS4 |  |  |  | MS4 |  |  |  | MS4 |  | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  | MS8 |  |  |  |  |  |  | D3.5
T3.2 New media |  |  |  |  | MS7 |  |  |  |  |  | MS7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS13 | MS10 |  |  | MS10 |  | D4.4 MS14

## Slide 12: Year 1 Effort
Partner | Cumul Direct | Cumul Indirect | Cumul Eligible | YEAR 1 Estimated Funding | YEAR 1 Planned Funding | % use
CERN | 234,503 | 130,801 | 365,304 | 249,763 | 169,480 | 147%
APO | 68,817 | 13,763 | 82,580 | 71,887 | 76,748 | 94%
QMUL | 59,986 | 35,992 | 95,978 | 64,185 | 116,727 | 55%
IMPERIAL | 25,694 | 15,416 | 41,110 | 27,492 | 41,521 | 66%
EGI.eu | 64,150 | 12,830 | 76,980 | 66,167 | 68,252 | 97%
Total | 453,150 | 208,802 | 661,952 | 479,494 | 472,728 | 101%

## Slide 13: Y2 Effort
Overall effort achieved in Q6 in PMs: per work package
Overall effort achieved in Q6 in PMs: per partner
Workpackage | Total plan (PM) | Dec | Jan | Feb | Total | Linear Plan | Q5 % achieved | Q6 % achieved
WP1 | 46 |  |  |  |  | 4.2 | 104% | 
WP2 | 64 |  |  |  |  | 5.8 | 90% | 
WP3 | 52 |  |  |  |  | 4.7 | 122% | 
WP4-M | 17 |  |  |  |  | 1.5 | 111% | 
WP2-UNF | 8 |  |  |  |  | 0.7 | 0% | 
WP4-UNF | 5 |  |  |  |  | 0.5 | 40% | 
Total | 192 |  |  |  |  | 17.5 | 98% | 
Partner | Total plan (PM) | Dec | Jan | Feb | Total | Linear Plan | Q5 % achieved | Q6 % achieved
CERN | 67 |  |  |  |  | 6.1 | 105% | 
APO | 34 |  |  |  |  | 3.1 | 87% | 
QMUL | 47 |  |  |  |  | 4.3 | 107% | 
IMPERIAL | 26 |  |  |  |  | 2.4 | 70% | 
EGI.eu | 18 |  |  |  |  | 1.6 | 112% | 
Total | 192 |  |  |  |  | 17.5 | 98% | 

## Slide 14: Expenditure Y1
CERN | Y1 plan | Y1 used | 
PMs | 24 | 24 | 100%
Personnel Costs | 135,543 | 193,234 | 143%
Travel | 11,547 | 12,531 | 109%
Subcontracting | 5,091 | 16,501 | 324%
Other | 6,545 | 3,494 | 53%
e-concertation meeting |  | 8,743 | ADDITIONAL BUDGET
Total Direct Costs | 158,726 | 234,503 | 148%
Indirect costs | 30,727 | 130,801 | 426%
Total Eligible Costs | 189,453 | 365,304 | 193%
Max. EC Requested Contribution | 169,480 | 249,763 | 147%
QMUL | Y1 plan | Y1 used | 
PMs | 17 | 14 | 
Personnel Costs | 79,389 | 52,553 | 66%
Travel | 9,337 | 3,173 | 34%
Subcontracting |  |  | 
Other | 20,364 | 4,260 | 21%
e-concertation meeting |  |  | ADDITIONAL BUDGET
Total Direct Costs | 109,091 | 59,986 | 55%
Indirect costs | 21,818 | 35,992 | 165%
Total Eligible Costs | 130,909 | 95,978 | 73%
Max. EC Requested Contribution | 116,727 | 64,185 | 55%

## Slide 15: Expenditure Y1
CERN | Y1 plan | Y1 used | 
PMs | 24 | 24 | 100%
Personnel Costs | 135,543 | 193,234 | 143%
Travel | 11,547 | 12,531 | 109%
Subcontracting | 5,091 | 16,501 | 324%
Other | 6,545 | 3,494 | 53%
e-concertation meeting |  | 8,743 | ADDITIONAL BUDGET
Total Direct Costs | 158,726 | 234,503 | 148%
Indirect costs | 30,727 | 130,801 | 426%
Total Eligible Costs | 189,453 | 365,304 | 193%
Max. EC Requested Contribution | 169,480 | 249,763 | 147%
EGI.eu | Y1 | Y1 used | 
PMs | 6.2 | 6.0 | 98%
Personnel Costs | 48,836 | 47,957 | 98%
Travel | 4,768 | 9,949 | 209%
Subcontracting |  |  | 
Other | 10,182 | 6,244 | 61%
e-concertation meeting |  |  | ADDITIONAL BUDGET
Total Direct Costs | 63,787 | 64,150 | 101%
Indirect costs | 12,757 | 12,830 | 101%
Total Eligible Costs | 76,544 | 76,980 | 101%
Max. EC Requested Contribution | 68,252 | 66,167 | 97%

## Slide 16: DoW Amendment
Budget changes proposal |  |  |  |  |  | 
A redistribution of budget to the central |  |  |  |  |  | 
budget(1) is envisaged to cover general |  |  |  |  |  | 
dissemination travel costs and provide a reserve |  |  |  |  |  | 
Creation of a Central Budget in EGI.eu hands for the travels of unfunded participants. |  |  |  |  |  | 
– QMUL OTHER COSTS Budget: 22k shift 15k |  |  |  | 15000 |  | 
Of which 5k to cover the Kings College sponsorship paid by EGI.eu |  |  |  |  |  | 
– Imperial TRAVEL Budget 10k: shift 5k |  |  |  | 5000 |  | 
INITIAL BUDGET TABLE |  |  |  |  |  | 
Participant number | Participant short name | Estimated eligible costs (whole duration of the project) |  |  |  | 
 |  | Coordination/ Support (A) | Management (B) | Other C | Total A+B+C | Requested EU contribution
1 | EGI.eu | 0.00 | 210,498.00 | 0.00 | 210,498.00 | 187,694.00
2 | QMUL | 359,998.00 | 0.00 | 0.00 | 359,998.00 | 320,998.00
3 | APO | 236,700.00 | 0.00 | 0.00 | 236,700.00 | 211,057.00
4 | Imperial | 128,054.00 | 0.00 | 0.00 | 128,054.00 | 114,181.00
5 | CERN | 520,995.00 | 0.00 | 0.00 | 520,995.00 | 466,070.00
 |  | 1,245,747.00 | 210,498.00 | 0.00 | 1,456,245.00 | 1,300,000.00
AMENDMENT N1 |  |  |  |  |  | 
Participant number | Participant short name | Estimated eligible costs (whole duration of the project) |  |  |  | 
 |  | Coordination/ Support (A) | Management (B) | Other C | Total A+B+C | Requested EU contribution
1 | EGI.eu | 20,000.00 | 210,498.00 | 0.00 | 230,498.00 | 187,694.00
2 | QMUL | 344,998.00 | 0.00 | 0.00 | 344,998.00 | 320,998.00
3 | APO | 236,700.00 | 0.00 | 0.00 | 236,700.00 | 211,057.00
4 | Imperial | 123,054.00 | 0.00 | 0.00 | 123,054.00 | 114,181.00
5 | CERN | 520,995.00 | 0.00 | 0.00 | 520,995.00 | 466,070.00
 |  | 1,245,747.00 | 210,498.00 | 0.00 | 1,456,245.00 | 1,300,000.00