## Slide 1: EMI 2 (Matterhorn) - Status
Cristina Aiftimiei (INFN)
EMI Release Manager
EGI TCB
EGI, 24 April 2012

## Slide 2: EMI 2 Release Candidate process
4 RCx – from Dec. 2011 to April 2012
Continuous Integration Builds – using ETICS
From „in-house“ deployment to deployment/testing on the EMI testbed campaigns
Repositories:
    http://emisoft.web.cern.ch/emisoft/dist/EMI/2/RCx

## Slide 3: EMI 2 preparation - Last steps
13 April 2012
  RC4 phase closed:
    SL5/x86_64 - 98% successful build rate
    SL6/x86_64 – 95% successful build rate
    Debian6:
      UI – with available clients
      ARC, UNICORE
  PTs testing RC4 versions of their component
  Deployment on EMI testbed
    To be finished April 18th
    Most product successfully tested
  Problematic products: Hydra, WMS (server)

## Slide 4: EMI 2 preparation - Last steps (cont.)
27 April 2012
  Products tested & certified
  Documentation ready
  Deployment on EMI testbed
Estimated release date – 7th May 2012

## Slide 5: EMI 2 content
All Products already in EMI 1
Hydra, WNoDeS, EMIR, CANL, Pseudonimity
EDGI bridges for all CEs
… but if Hydra and WMS do not pass certification by the release date, they will be released later with an update

## Slide 6: EMI 2 backward incompatibilities
No interface changes
Packaging changes in
  gridsite
  cgsi_gsoap
  dCache
Mainly to comply with existing EPEL package names

## Slide 7
Thank you
EMI is partially funded by the European Commission under Grant Agreement INFSO-RI-261611